## General
[12 empty] | Project No: |  |  | Project Title: |  |  |  | Date:
[12 empty] | EEPZ252131 |  |  | RENOVATE CONVERT 50th 49th SQ OPS, B230 |  |  |  | 2026-01-22
LINE NO. | ITEM DESCRIPTION | SPEC REF | NUMBER OF COPIES REQUIRED | [8 empty] | DATE KTR REQUIRES APPROVAL | DATE RECEIVED KTR | DATE TO CIVIL ENG | DATE RECEIVED FROM CE | DATE CONTRACTOR NOTIFIED APR DISAPR | CONTRACT RESUBMIT DUE | CONTRACT RESUBMITTAL RECEIVED | FINAL APPROVAL RCVD KTR NOTIFIED
|  |  | Certificate of Compliance | Shop Drawings | Samples | Color Selction | Manufacturer's Recommendations | Manufacturer's Warranty | Catalog Data | Operating Instructions | Other
GENERAL
1 | Work/Construction Plan | BASIC | [8 empty] | X
2 | Phasing Plan | BASIC | [8 empty] | X
3 | Demolition Plan | BASIC | [8 empty] | X
4 | As-Built Drawings | BASIC | [8 empty] | X
5 | Progress Schedule | BASIC | [8 empty] | X
6 | Guarantees and Warranties | BASIC | [8 empty] | X
7 | Superintendent's Qualifications and Experience | BASIC | [8 empty] | X
SCHEDULE OF MATERIAL SUBMITTALS

## Environmental
[12 empty] | Project No: |  |  | Project Title: |  |  |  | Date:
[12 empty] | EEPZ252131 |  |  | RENOVATE CONVERT 50th 49th SQ OPS, B230 |  |  |  | 2026-01-22
LINE NO. | ITEM DESCRIPTION | SPEC REF | NUMBER OF COPIES REQUIRED | [8 empty] | DATE KTR REQUIRES APPROVAL | DATE RECEIVED KTR | DATE TO CIVIL ENG | DATE RECEIVED FROM CE | DATE CONTRACTOR NOTIFIED APR DISAPR | CONTRACT RESUBMIT DUE | CONTRACT RESUBMITTAL RECEIVED | FINAL APPROVAL RCVD KTR NOTIFIED
|  |  | Certificate of Compliance | Shop Drawings | Samples | Color Selction | Manufacturer's Recommendations | Manufacturer's Warranty | Catalog Data | Operating Instructions | Other
GENERAL
8 | Appropriate SDS | BASIC | [8 empty] | X
9 | Green Procurment Report | BASIC | [8 empty] | X
10 | Hazardous waste report | BASIC | [8 empty] | X
11 | Hazardous Material Report (AF Form 3000) | BASIC | [8 empty] | X
12 | Air Emission Source Specifications for equipment removed | BASIC | [8 empty] | X
13 | Recycled Material Report/Construction Debris report | BASIC | [8 empty] | X
14 | Storm Water Pollution Prevention Plan with Best Management Practices Identified | BASIC | [8 empty] | X
15 | Weekly Inspection Reports for Projects | BASIC | [8 empty] | X
16 | State Notification for Demolition & Renovation 10 day notice | BASIC | [8 empty] | X
17 | Work Plan | BASIC | [8 empty] | X
18 | Copy of ACM Disposal Manifest | BASIC | [8 empty] | X
SCHEDULE OF MATERIAL SUBMITTALS

## Architectural
[12 empty] | Project No: |  |  | Project Title: |  |  |  | Date:
[12 empty] | EEPZ252131 |  |  | RENOVATE CONVERT 50th 49th SQ OPS, B230 |  |  |  | 2026-01-22
LINE NO. | ITEM DESCRIPTION | SPEC REF | NUMBER OF COPIES REQUIRED | [8 empty] | DATE KTR REQUIRES APPROVAL | DATE RECEIVED KTR | DATE TO CIVIL ENG | DATE RECEIVED FROM CE | DATE CONTRACTOR NOTIFIED APR DISAPR | CONTRACT RESUBMIT DUE | CONTRACT RESUBMITTAL RECEIVED | FINAL APPROVAL RCVD KTR NOTIFIED
|  |  | Certificate of Compliance | Shop Drawings | Samples | Color Selction | Manufacturer's Recommendations | Manufacturer's Warranty | Catalog Data | Operating Instructions | Other
GENERAL
19 | Interior Wall Insulation | BASIC |  |  |  |  | X | X | X
20 | Exterior Wall Insulation | BASIC |  |  |  |  | X | X | X
21 | Ceiling Insulation | BASIC |  |  |  |  | X | X | X
22 | Exterior Wall Assemblies | BASIC |  |  | X | X | X | X | X
23 | Cement/Concrete | BASIC |  |  |  |  | X | X | X | X
24 | Hard Surface Transition Strips | BASIC |  |  | X | X | X | X | X
25 | Concrete Stain | BASIC |  |  | X | X | X | X | X | X
26 | Epoxy | BASIC |  |  | X | X | X | X | X | X
27 | Floor Tiles | BASIC |  |  | X | X | X | X | X
28 | Cementitious Backerboard | BASIC |  |  |  |  | X | X | X
29 | Wall Tiles | BASIC |  |  | X | X | X | X | X
30 | Profiles/Transitions (For Inside Wall Corners and Floor/Wall Transitions) | BASIC |  |  | X | X | X | X | X
31 | Grout | BASIC |  |  | X | X | X | X | X
32 | LVT | BASIC |  |  | X | X | X | X | X
33 | Carpet | BASIC |  |  | X | X | X | X | X
34 | Rubber Cove Base | BASIC |  |  | X | X | X | X | X
35 | Interior Man Doors | BASIC |  | X
| 1. Doorframes | BASIC |  |  |  | X | X | X
| 2. Cased Openings | BASIC |  |  |  |  | X | X
| 3. Doors | BASIC |  |  |  | X | X | X | X
| 4. Hardware | BASIC |  |  |  |  | X | X
| 5. Thresholds and Weatherstripping | BASIC |  |  |  |  | X | X
36 | Concrete Masonry Unit (CMU) | BASIC |  |  | X | X | X | X | X
37 | Gypsum Wallboard | BASIC |  |  |  |  | X | X | X
38 | Galvanized Steel Furring | BASIC |  |  |  |  | X | X | X
39 | Galvanized Steel Studs & Framing | BASIC |  | X |  |  | X | X | X
40 | Galvanized Steel Bracing Strips | BASIC |  | X |  |  | X | X | X
41 | Gypsum Tape | BASIC |  |  |  |  | X | X | X
42 | Gypsum Plaster | BASIC |  |  |  |  | X |  |  | X
43 | Suspended Ceiling | BASIC |  | X
| 1. Ceiling Grid | BASIC |  |  |  | X | X | X | X
| 2. Ceiling Tiles | BASIC |  |  |  | X | X | X | X
| 3. Grid Supports | BASIC |  |  |  |  | X | X | X
| 4. Seismic Supports | BASIC | X |  |  |  | X | X | X
44 | Exterior Wall Primer/Paint | BASIC |  |  | X | X | X | X | X
45 | Interior Wall Primer/Paint | BASIC |  |  | X | X |  | X | X
46 | Exterior Door Primer/Paint | BASIC |  |  | X | X | X | X | X
47 | Interior Door Primer/Paint | BASIC |  |  | X | X |  | X | X
48 | Bathroom Vanity | BASIC |  |  |  |  | X | X | X
49 | Vanity Handles | BASIC |  |  | X | X | X | X | X
50 | Cabinets | BASIC |  |  | X | X | X | X | X
51 | Cabinets Hardware | BASIC |  |  | X | X | X | X | X
52 | Shelving | BASIC |  |  | X | X | X | X | X
53 | Solid SurfaceCountertops/ Backsplash | BASIC |  |  | X | X | X | X | X
54 | Stall Partitions | BASIC |  | X |  | X | X | X | X
55 | Grab Bars | BASIC |  |  |  |  | X | X | X
56 | Mirrors | BASIC |  |  |  |  | X | X | X
57 | Napkin/Tampon Recepticles | BASIC |  |  |  |  | X | X | X
58 | Toilet Tissue Dispenser | BASIC |  |  |  |  | X | X | X
59 | Hardware | BASIC |  |  |  |  | X | X | X
60 | Fasteners | BASIC |  |  |  |  | X | X | X
SCHEDULE OF MATERIAL SUBMITTALS

## Civil
[12 empty] | Project No: |  |  | Project Title: |  |  |  | Date:
[12 empty] | EEPZ252131 |  |  | RENOVATE CONVERT 50th 49th SQ OPS, B230 |  |  |  | 2026-01-22
LINE NO. | ITEM DESCRIPTION | SPEC REF | NUMBER OF COPIES REQUIRED | [8 empty] | DATE KTR REQUIRES APPROVAL | DATE RECEIVED KTR | DATE TO CIVIL ENG | DATE RECEIVED FROM CE | DATE CONTRACTOR NOTIFIED APR DISAPR | CONTRACT RESUBMIT DUE | CONTRACT RESUBMITTAL RECEIVED | FINAL APPROVAL RCVD KTR NOTIFIED
|  |  | Certificate of Compliance | Shop Drawings | Samples | Color Selction | Manufacturer's Recommendations | Manufacturer's Warranty | Catalog Data | Operating Instructions | Other
GENERAL
NONE
SCHEDULE OF MATERIAL SUBMITTALS

## Mechanical
[12 empty] | Project No: |  |  | Project Title: |  |  |  | Date:
[12 empty] | EEPZ252131 |  |  | RENOVATE CONVERT 50th 49th SQ OPS, B230 |  |  |  | 2026-01-22
LINE NO. | ITEM DESCRIPTION | SPEC REF | NUMBER OF COPIES REQUIRED | [8 empty] | DATE KTR REQUIRES APPROVAL | DATE RECEIVED KTR | DATE TO CIVIL ENG | DATE RECEIVED FROM CE | DATE CONTRACTOR NOTIFIED APR DISAPR | CONTRACT RESUBMIT DUE | CONTRACT RESUBMITTAL RECEIVED | FINAL APPROVAL RCVD KTR NOTIFIED
|  |  | Certificate of Compliance | Shop Drawings | Samples | Color Selction | Manufacturer's Recommendations | Manufacturer's Warranty | Catalog Data | Operating Instructions | Other
GENERAL
61 | HVAC TAB Report | BASIC | X |  |  |  | X |  | X |  | X
62 | Duct Insulation | BASIC |  | X |  |  | X | X | X
63 | Metal Ductwork | BASIC | X | X |  |  | X | X | X | X
64 | Dampers | BASIC |  | X |  |  | X | X | X | X
65 | Diffusers | BASIC |  | X |  | X | X | X | X | X
66 | Grilles | BASIC |  | X |  | X | X | X | X | X
67 | Controls | BASIC | X | X |  |  | X | X | X | X
68 | Split Systems | BASIC | X | X |  |  | X | X | X | X
69 | Exahust Fan | BASIC | X | X |  |  | X | X | X | X
70 | Lavatories | BASIC |  | X |  | X | X | X | X | X
71 | Faucets | BASIC |  | X |  |  | X | X | X | X
72 | Piping | BASIC |  | X |  |  | X | X | X
73 | Pipe Fittings | [5 empty] | X | X | X
74 | Water Closets | BASIC |  |  |  | X | X | X | X | X
75 | Flush Handles | BASIC |  |  |  | X | X | X | X | X
76 | Carriers | BASIC |  |  |  |  | X | X | X
77 | Hardware | BASIC |  |  |  |  | X | X | X
78 | Fasteners | BASIC |  |  |  |  | X | X | X
79 | Drinking Fountain | BASIC |  |  |  |  | X | X | X | X
80 | Showers | BASIC | X |  |  |  | X | X | X | X
81 | Water Lines | BASIC |  |  |  |  | X | X | X
82 | Vents | BASIC |  |  |  |  | X | X | X
83 | Traps | BASIC |  |  |  |  | X | X | X
84 | Copper Caps | BASIC |  |  |  |  | X | X | X
85 | Drains | BASIC |  |  |  |  | X | X | X
86 | Shut-off Valves | BASIC |  |  |  |  | X | X | X | X
SCHEDULE OF MATERIAL SUBMITTALS

## Electrical
[12 empty] | Project No: |  |  | Project Title: |  |  |  | Date:
[12 empty] | EEPZ252131 |  |  | RENOVATE CONVERT 50th 49th SQ OPS, B230 |  |  |  | 2026-01-22
LINE NO. | ITEM DESCRIPTION | SPEC REF | NUMBER OF COPIES REQUIRED | [8 empty] | DATE KTR REQUIRES APPROVAL | DATE RECEIVED KTR | DATE TO CIVIL ENG | DATE RECEIVED FROM CE | DATE CONTRACTOR NOTIFIED APR DISAPR | CONTRACT RESUBMIT DUE | CONTRACT RESUBMITTAL RECEIVED | FINAL APPROVAL RCVD KTR NOTIFIED
|  |  | Certificate of Compliance | Shop Drawings | Samples | Color Selction | Manufacturer's Recommendations | Manufacturer's Warranty | Catalog Data | Operating Instructions | Other
GENERAL
87 | Conductor | BASIC | [8 empty] | X
88 | Conduit | BASIC | [8 empty] | X
89 | Riser Clamps | BASIC | [8 empty] | X
90 | Junction Boxes | BASIC |  |  |  |  | X | X | X
91 | Electric Metallic Tubing | BASIC | [8 empty] | X
92 | Switch Devices | BASIC |  |  |  | X | X | X | X | X
93 | Receptacles | BASIC |  |  |  |  | X | X | X
94 | Faceplates | BASIC |  |  |  | X | X | X | X
95 | Wall Jacks | BASIC |  |  |  |  | X | X | X
96 | Cable Supports | BASIC | [8 empty] | X
97 | Circuit Breakers | BASIC |  | X |  |  | X | X | X | X
98 | Safety Swtiches | BASIC |  | X |  |  | X | X | X | X
99 | Interior LED Fixtures | BASIC |  | X |  |  | X | X | X | X
100 | Seismic Wire Support For Light Fixtures | BASIC |  |  |  |  | X | X | X | X
101 | Fixture Whips | BASIC |  |  |  |  | X | X | X
102 | Occupancy Sensor | BASIC |  | X |  |  | X | X | X | X
103 | Electrical Identification/Nameplates/Markers | BASIC | [8 empty] | X
104 | Photometric Analysis | BASIC | [8 empty] | X
SCHEDULE OF MATERIAL SUBMITTALS

## Special Systems
[12 empty] | Project No: |  |  | Project Title: |  |  |  | Date:
[12 empty] | EEPZ252131 |  |  | RENOVATE CONVERT 50th 49th SQ OPS, B230 |  |  |  | 2026-01-22
LINE NO. | ITEM DESCRIPTION | SPEC REF | NUMBER OF COPIES REQUIRED | [8 empty] | DATE KTR REQUIRES APPROVAL | DATE RECEIVED KTR | DATE TO CIVIL ENG | DATE RECEIVED FROM CE | DATE CONTRACTOR NOTIFIED APR DISAPR | CONTRACT RESUBMIT DUE | CONTRACT RESUBMITTAL RECEIVED | FINAL APPROVAL RCVD KTR NOTIFIED
|  |  | Certificate of Compliance | Shop Drawings | Samples | Color Selction | Manufacturer's Recommendations | Manufacturer's Warranty | Catalog Data | Operating Instructions | Other
GENERAL
104 | Sprayed Fireproofing | BASIC | X |  |  |  | X | X | X
105 | Firestopping | BASIC | X |  |  |  | X | X | X
106 | Fiber Card (Notifier 320 Capatable) | BASIC | X | X |  |  | X | X | X | X
107 | Heat/Smoke Detectors | BASIC | X | X |  |  | X | X | X
108 | Strobes and Horns, ADA | BASIC | X | X |  |  | X | X | X
109 | Preliminary Testing Reports | BASIC | [8 empty] | X
110 | Acceptance Testing Reports | BASIC | X | [7 empty] | X
SCHEDULE OF MATERIAL SUBMITTALS

## Other&Misc
[12 empty] | Project No: |  |  | Project Title: |  |  |  | Date:
[12 empty] | EEPZ252131 |  |  | RENOVATE CONVERT 50th 49th SQ OPS, B230 |  |  |  | 2026-01-22
LINE NO. | ITEM DESCRIPTION | SPEC REF | NUMBER OF COPIES REQUIRED | [8 empty] | DATE KTR REQUIRES APPROVAL | DATE RECEIVED KTR | DATE TO CIVIL ENG | DATE RECEIVED FROM CE | DATE CONTRACTOR NOTIFIED APR DISAPR | CONTRACT RESUBMIT DUE | CONTRACT RESUBMITTAL RECEIVED | FINAL APPROVAL RCVD KTR NOTIFIED
|  |  | Certificate of Compliance | Shop Drawings | Samples | Color Selction | Manufacturer's Recommendations | Manufacturer's Warranty | Catalog Data | Operating Instructions | Other
GENERAL
NONE
SCHEDULE OF MATERIAL SUBMITTALS

## HAZMAT Tracking Sheet
Contractor Hazardous Materials Usage Tracking Form
Return this form to Contracting/Project Manager with Manufacturers original SDS
EEPZ252131 |  | RENOVATE CONVERT 50th 49th SQ OPS, B230 |  |  | Contract #
Start Date: |  | End Date: |  |  | Cotractor:
Product Name as seen on SDS Process (How is material used) |  | Part # | Manufacturer | Type of Container | Size of Container | Total Quantity Used | EESOH MSN
1
Process:
2
Process:
3
Process:
4
Process:
5
Process:
6
Process:
7
Process:
8
Process:
9
Process:
10
Process:
11
Process:
12
Process:
13
Process:
14
Process:
15
Process:
16
Process:
17
Process:
18
Process:
19
Process:
20
Process:
21
Process:
22
Process:
23
Process:
24
Process:
25
Process:
26
Process:
27
Process:
28
Process:

## Example and Instructions
WORKSHEET INSTRUCTIONS
BLOCK | DESCRIPTION | INFORMATION REQUIRED
A | Project Number | Project number or Opportunity number assigned to the project by Civil Engineering.
B | Project Title | The title of the project.
C | Contract Number | The contract number or delivery order assigned by contracting.
D | Product Name | The name of the product as listed on the SDS.
E | Process | A Brief description of the work performed with each material.
F | Part # | The part number as listed on the SDS.
G | Manufacturer | The name of the Manufacturer of the product (not the distributor)
H | Type of Container | The type of container that the product comes in. Example: can, barrel, bottle, container, cylinder, drum, etc…
I | Size of Container | Size as listed on container. Example: oz, lbs, Liter, Quart, Gallon, etc…
J | Total Quantity Used | This will be the amount that you anticipate using for the first submission. At the conclusion of the project you will need to provide a final list with updated quantities.
K | EESOH MSN | This is the Material Stock Number assigned for EESOH-MIS tracking. (The Air Force Hazardous Materials Manager will provide this number)
NOTE: Complete the HAZMAT Tracking Sheet located on the first TAB of this Excel spreadsheet with all hazardous materials to be used during the duration of the construction project. Once completed, save the sheet as a .pdf file and submit to the contracting officer with an AF Form 3000 Submittal form. This data will need to be submitted prior to construction start. When construction is complete, you will submit a final revised report with updated quanties.