## Sheet1
RFI # | RFI | RFI Response
1 | Is the Non-manufacturer Rule going to be followed where both the dealer and manufacturer(s) need to be a small business OR only the dealership is required to be a small? | BLUF: The nonmanufacturer rule requires both to be small business. Exaplanation: If the dealer is the small business and the manufacturer is a large business, this would require a Waiver from Small Business Adminsitration which is what CONS is trying to prevent as the process for a waiver is time consuming and not guaranteed to be obtained.
2 | Is the floor raised? | Yes, 27"
3 | Please verify the quantity of furniture required in the SOW. (For instance, Room 14 requires 19 cubicles, drawers, chairs, and overhead cabinets yet 20 desks). | The rough sketch we had was for 19 desks. The SOW has been updated to reflect this.
4 | For room 10, do you require cubes or cased goods? | Cased goods. Looking for more along the lines of training desks not standard work desks.
5 | Do we have a CAD (Floor plan) drawing? | Drawing has been provided.
6 | Is a date extension possible? In order to provide Fixed Firm Pricing, Design may need more time depending on when the questions are answered. | An extension will be provided.
7 | Please confirm Rooms 10, 12, and 14 are the highlighted rooms in the attachment and no other work is requried. | 10 ,12, and 14 are the rooms being renovated. Only work that may be required outside would be electrical if a circuit is needed.
8 | Executive style is referenced - is this for all desks or just rooms 10 & 12? | disregard just looking for tables to perform training activities in a classroom setting in room 12. Room 10 just maximize cubicle furniture.
9 | Can you please further explain "executive style"? | disregard executive furniture.
10 | Overall layout - are the requirements to follow the plans provided or provide suggested layouts? Are D tops required for desking? | suggestions can be made to maximize space. D tops are not required for desking.
11 | Room 10 specifices 4 cubicles, 4 stationary desks, design looks to be (4) surfaces with 2 stations - is the ask for (4) people in (4) cubes with cubicle walls in room 10? | Will be 4 workstaitons for 4 people to be able to occupy with just NIPR capability.
12 | Room 12, are you open to larger desks widths? Making the assumption it's 2 people per 60"w, can we provide something larger? | Larger widths will be fine.
13 | Room 14, the swinging doors - are those hard wall doors or furniture system doors; are swinging doors required for the cubicles? Are there specified heights? Do NIPR and SIPR need to be separated by a certain distance? It looks like there are random cubicle wing panels throughout - are those required? | Those hard doors are on the system furniture. Not a requirement for new furniture. Specified cubicle heights around 60-66". High enough to ensure overhead storgae but does not require doors. Willing to allow the ability to open up the space some. SIPR is not in the space area so the question is not applicable.
14 | Are there any upgrade preferences for all task chairs? Adjustable arms, lumbar support, seat tilt limiter? | adjustable arms, but not overly required for other upgrades. Open to suggestions from vendors/contractor.
15 | Is the power required in the panels? If so, how many receptacles per workstation? If so, is powered required in the baseline, or base and belt line? | Minimum of 2 duplex receptacles placed on each side of the desk to maximize usable desk space.
16 | Is there an install date you're working towards? | no specific date, just before end of fiscal year, 30 September 2026, would be preferred
17 | There is a request to not cover existing wall accessories, is there a plan that provides these? | No layout plan, but pre-installation walk through can be arranged as it is the contractor's responsibility to assess the area for accuracy and discprepancies prior to beginning work.
18 | Are you able to provide layout of how you are wanting the furniture setup to be? | Can provide possible suggestions, but open to suggestions from contractors
19 | What brand specified for this project? | No specific brand.
20 | What are the room dimensions? | Provided in the AutoCAD Drawing.
21 | Are phsycial modular walls required for this project, or is it limited to furniture only? | would like cube walls to break up work spaces, plus provide pssible mounting spaces for storage
22 | Please provide additional details for worksurfaces and cabinets: dimensions (W x D x H)and any specifications. | SOW has been updated with dimensions.
23 | Can we deliver and install the product during business hours? | yes, personnel will be available between 0730-1630.
24 | Is there a loading dock? | There is a loading dock for building 400
25 | If there isn't a loading dock, where will we offload the truck? | n/a
26 | Apprxoimately how far is it from the truck offload site to the install location? | 500 feet with straight open hallways.
27 | Are there any stairs that the product will need to go up or down to reach the install location? | no stairs
28 | Will we use a passenger or reight elevator for delivery to the install location, if applicable? | not needed on the first floor
29 | Will our electrician need to pull new circuits from the electrical panel or will we attach to existing power junction boxes at walls/columns (reuse the existing electrical that is being used fro the existing panel system? | can reuse the maximum, but may need to pull a a circuit or 2.
30 | Does 50 CES have a list of approved electricians that they would like us to use? | CE does not have a list of approved electricians. Still suggest submitting the electrician for approval through CONS office before proceeding.
31 | Should the initial design of all furnishings reflect what is shown in Attachment 2 (knowing that the awarded contractor is responsible to complete architectual plans and final installation plans during the post award site visit)? | not needed. We are fine with seeing any plans that are provided and suggested by contractors.
32 | Are the seating specifications open to upholstered and/or mesh seats backs, or a combination of mesh and upholstered? | Updated in the SOW.
33 | Power - Will the station occupants equipment connect directly into the existing wall or raised floor outlets or are station electrical infeeds required that connect directly to the building circuit panel? | in room 14 the existing furniture should be powered directly from the panel and would need to reqired. Rooms 10 and 12 can be done from the wall/below floor.
34 | Power - Are desktop 110 & USB power module needed or required at any of the locations? | All worstations are 110 . USB are not a requirement.
35 | Panel Height - Is there a preference to the panel height or does it vary between offices? | it varies between desk/work areas. Refer to RFI 13 for estimated cubicle/panel height.
36 | Are the drawer dimensions listed in the standard order: width, depth, and height? If yes, can you confirm which measurement is width, which is depth, and which is height? If no, can you clarify the correct order of the dimensions 1.5, 2, amd 3? | Standard drawer size. Will consider whatever design you provide/suggest to maximize space.
37 | Will the drawer go alongisde the table? If yes, can you confirm the available space next to the table? If no, will it go under the table instead? | Under the table, but we will consider alternate design if presented.