## Sheet1
| UPS Detail | UPS Detail | UPS Detail | UPS Detail | UPS Detail | UPS Detail | UPS Detail | UPS Detail | UPS Detail | UPS Detail | UPS Detail | UPS Detail | UPS Detail | UPS Detail | UPS Detail | UPS Detail | UPS Detail | UPS Detail | UPS Detail | UPS Detail | UPS Detail | UPS Detail | UPS Detail | UPS Detail
UPS Make | Riello | Eaton | Eaton | Riello | GE | Jovy Atlas | Riello | JovyAtlas | Wartsila | Reillo | APC | Reillo | IES | JovyAtlas | Reillo | Vertiv | Reillo | APC | APC | APC | APC | APC | APC | Riello
UPS Model | Sentryum S3M 10-60XTD | 9390 | 9390 | Master Sentinel Dual | LP Series | JovyStar+ | Master HP | JovyStar BAX5706 | JovyStar | Master HP | Smart-UPS | Master HP | 1395-V1 | Compact S | CSPTK10AA5 | EXS000010KTH1AFN01000 | UPS MST 60 | SRT192RMBPUS | SRT192RMBPUS | SRT5KRMXLTUS | SRT5KRMXLTUS | SRT5KRMXLTUS | SRT5KRMXLTUS | MULTI SENTRY MST 15-A0
Serial # | AR51UT300660004 | EF295CAB06 | EF293CAB01 | AA29UT111360002 | L60201617B644A | 119334 | MH11UT905180005 | 000313 | 141206 | MH12VT906980005 | AS1945233512 | MH12UT906820005 | 202011431 | 148520 | MR31UT753260006 | 2101202195220500000E | MH08UT899390006 | N12423110054 | N12423110039 | N12436140082
KVA | 10 | 40 | 40 | 8 | 20 | 15 | 10 | 250 | 15 | 10 | 10 | 10 | 28 | 30 | 10 | 10 | 60 | 5 | 5 | 5 | 5 | 5 | 5 | 15
Sealed Battery Jar Qty | 120 | 40 | 40 | 20 | Internal | Internal | 80 | 64 | 60 | 80 | (Internal 4) | 80 | 96 | 120 | 40 | 32 | Internal | Internal | Internal | Internal | Internal | Internal | Internal
Flooded Batt Cell Qty
Battery Make | Riello | CTM | CTM | CTM |  |  | CSB | GNB Exide | Jovy | CSB | Vision | CSB | GNB |  | Riello | Vertiv | Reillo | APC | APC | APC | APC | APC | APC | Riello
Battery Model |  | CTL 55-12 | CTL 55-12 | CTL 26-12 |  |  | GPL 1272F2 | Sprinter XP12V3000 |  | GPL 1272F2 | CP1270 | GPL 1272F2 | Sonnenschein A602/750 |  | BBXSPW240VACM4
Battery replacement or installation date |  | Replace batteries: 07/23/2025 | Replace batteries: 07/23/2025 |  |  |  | Replace batteries: 05/15/2025 | Replace batteries: planned 2026 | Replace batteries: 05/16/2025 |  | need to be replaced | Replace batteries: 05/17/2026 |  |  |  | Replace batteries: in beginning of 2026 |  | install: 24April2025 | install: 24April2025 | install: not a exact date but in April or Mai2025 | install: not a exact date but in April or Mai2025 | install: 16April2025 | install: 16April2025
Bldg # | 15 | 45 (Radar Equip) | 45 (Radar Equip) | 47 | 47 | 47 | 211 | 212 | 366 | 455 | 690 | 774 | 24 | 3030 | 967 | 577 | 1116 | 1116 | 1116 | 88 | 88 | 512 | 512 | 616
Room # | 1 | 1st Fl Comms Rm | 1st Fl Comms Rm | 3rd Fl Comms Rm |  |  | Comms Room | Room 114 | 1 | 1 | 1.14 | 1 |  | Electrical room 119 | 1 | 1 | Comm RM | Comm RM | Comm RM | Comm RM | Comm RM | Comm Room | Comm Room | Comm Room
Location | Spangdahlem AB Germany | Spangdahlem AB Germany | Spangdahlem AB Germany | Spangdahlem AB Germany | Spangdahlem AB Germany | Spangdahlem AB Germany | Spangdahlem AB Germany | Spangdahlem AB Germany | Spangdahlem AB Germany | Spangdahlem AB Germany | Spangdahlem AB Germany | Spangdahlem AB Germany | Spangdahlem AB Germany | Spangdahlem AB Germany | Spangdahlem AB Germany | Spangdahlem AB Germany | Volkel AB, Netherlands | Volkel AB, Netherlands | Volkel AB, Netherlands | Geilenkirchen AB, Germany | Geilenkirchen AB, Germany | Buechel AB, Germany | Buechel AB, Germany | Buechel AB, Germany