## SOS&S
PRICING SCHEDULE FOR:
USCGC CALHOUN (WMSL-418) DOCKSIDE AVAILABILITY FQ4 FY2026
ITEM | DESCRIPTION | UNIT PRICE | UNIT | QTY | EXTENDED PRICE
D-001 | Stern Boat Launch and Recovery, Level II |  | JOB
D-002 | Talon Grid (Type 18-08), Inspect and Test |  | JOB
D-003 | Cargo Handling Elevator, Annual Inspection and Test, Perform |  | JOB
D-004 | Incinerator, Inspect and Test |  | JOB
D-005 | Oily Water Separator (OWS) System, Inspect and Groom |  | JOB
D-006 | Fire Detection System, Inspect and Test |  | JOB
D-007 | Deck Covering (Slip-Resistant) Flight Deck, Renew |  | JOB
D-008 | Deck Covering (Slip-Resistant) Hangars, Renew |  | JOB
D-009 | Deck Covering (Slip-Resistant), Renew |  | JOB
D-010 | Tenting, Provide |  | JOB
D-011 | Tanks (Aviation Fuel Service), Clean and Inspect |  | JOB
D-012 | Tanks (Aviation Fuel Stowage and Overflow), Clean and Inspect |  | JOB
O-013 | Tanks, Preserve Full (100%) |  | JOB
O-014 | Tanks, Partial Preserve |  | JOB
D-015 | Grey Water Holding Tank(s) and Lift Stations, Clean and Inspect |  | JOB
D-016 | Sewage Holding Tank(s), Clean and Inspect |  | JOB
D-017 | Tanks (MP Fuel Storage and Overflow), Clean and Inspect |  | JOB
D-018 | Tanks (Oily Waste), Clean and Inspect |  | JOB
O-019 | Welding, Provide (General) |  | JOB
D-020 | Sewage System, Modify |  | JOB
D-021 | Sewage Piping, Clean and Flush |  | JOB
D-022 | Fire Prevention, Provide |  | JOB
O-00Z | Laydays |  | Day | 5 | #VALUE!
| Total Price of Definite Items |  |  |  | #VALUE!
| Total Price of Option Items |  |  |  | #VALUE!
| Total Price of Definite and Optional Items |  |  |  | #VALUE!

## CostEstimateBreakdowns
| Composite Labor Rate | 55
| Assumed G&A Factor | 15%
| Assumed Profit Factor | 10% |  |  |  | Direct Labor | [9 empty] | Direct Material/Subs Cost
ITEM | DESCRIPTION | UNIT PRICE | Sub-Contracted (put a "1" in the blank) | Total Labor Hours | Total Material & Subs (cost + G&A + profit) | Eng Tech | Machinest/Pipe Fitter | Electrician | Shipfitter | Welder | Firewatch | Insulator/Lagger | Painter | Gen Labor/Helper/Rigger | Supt/QA/NDT | Mat/Sub Cost 1 | Mat/Sub Cost 2 | Mat/Sub Cost 3 | Mat/Sub Cost 4 | Lab Rate | Area | WorkItemID | WIFileID | LoadData
[20 empty] | 62 | Baltimore, MD
[20 empty] | 52 | Biloxi, MS
[20 empty] | 56 | Boston, MA
[20 empty] | 50 | Charleston, SC
[20 empty] | 60 | Corpus Christi, TX
[20 empty] | 51 | Hampton Roads
[20 empty] | 64 | Honolulu, HI
[20 empty] | 55 | Houston, TX
[20 empty] | 56 | Los Angeles, CA
[20 empty] | 55 | Median Rate
[20 empty] | 49 | Miami
[20 empty] | 50 | Narragansett Bay, RI
[20 empty] | 55 | New London, CN
[20 empty] | 45 | New Orleans
[20 empty] | 62 | NYNY
[20 empty] | 49 | Panama City, FL
[20 empty] | 60 | Philadelphia, PA
[20 empty] | 51 | Portland, ME
[20 empty] | 57 | Portland, OR
[20 empty] | 55 | San Diego, CA
[20 empty] | 67 | San Francisco, CA
[20 empty] | 55 | Santa Barbara, CA
[20 empty] | 55 | SE North Carolina
[20 empty] | 65 | Seattle, WA
[20 empty] | 48 | Tampa-St. Petersburg
[20 empty] | 60 | Wilmington, DE

## CostEstimateTemplate
1