## Material Submittals Schedule
Project Number: MAHG251046 | [8 empty] | Project Title: Repair Replace Basketball Floor | [9 empty] | Solicitation / Contract Number: Attachement 4 - FA301026R0009
Line Number | (To be completed by Project Engineer) | [13 empty] | (To be completed by Contract Administrator)
|  | Number of Copies Required (if not electronically submitted) | [20 empty] | Remarks
| Item or Description of Item, Contract Reference, Type of Submittal | Certificate of Compliance | Shop Drawings | Samples | Color Selection | Manufacturer's Recommendation | Warranty-Manufacturer and/or Workmanship | Catalog Data | Operating Instructions | Schedules, Listings, Reports, Plans | Technical Data | Test Reports | Field Reports | Required Submission Date | Date Received in Contracting | Date to Civil Engineering | Return Suspense Date | Submittal Numbers | Date Contractor Notified |  | Contractor Resubmittal | Final Approval
[19 empty] | Approved | Disapproved
1 | HazMat Questionnaire | [9 empty] | 3 | 3 |  | 5 Days Prior to Start Date
2 | HazMat MSDS | [9 empty] | 3 | 3 |  | 5 Days Prior to Start Date
3 | HazMat Reporting Entry Form | [9 empty] | 3 | 3 |  | 5 Days Prior to Start Date | [8 empty] | Submit Final Quantities
4 | HazMat Reporting entry Form | [9 empty] | 3 | 3 |  | End of Contract
5 | Recycling and Landfill Report | [9 empty] | 3 | 3 |  | End of Contract
6 | Warranty (Manufacture's) | [9 empty] | 3 | 3 |  | End of Contract
7 | 1-Year Warranty (Contractor's) | [9 empty] | 3 | 3 |  | End of Contract
8 | 09 62 40 Modular Athletic Flooring |  | 3 | 3 | 3 | [5 empty] | 3 |  |  | 10 Days Following NTP
9 | 09 64 66 Wood Flooring - Raquetball Court |  | 3 | 3 | 3 | [5 empty] | 3 |  |  | 10 Days Following NTP
10 | 09 65 13 Resiliant base and Accessories |  |  | 3 | 3 | [5 empty] | 3 |  |  | 10 Days Following NTP
| Layout of Court Markings for each Sport |  | 3 | [10 empty] | 10 Days Following NTP
11
12
13
14
15
16
17
18
19
20
21
22
23
8
9
10
10
11
12
13
11
15
16
12
12
13
14
15
20
14
15
16
17
18
19
20
21
22
23
24
25
Note on O4: Enter the due date from the Contractor (MM/DD/YY)
Note on P4: Enter the date received from the Contractor. (MM/DD/YY)
Note on Q4: Enter the date submittal was given to CE for review. (MM/DD/YY)
Note on R4: Enter the date the submittal is due back from CE (MM/DD/YY)
Note on S4: Enter the Submittal Number
Note on V4: Enter Resubmittal Number
Note on W4: Enter the submittal final approval date (MM/DD/YY)
Note on T5: Enter date the Contractor was notified of submittal approval (MM/DD/YY)
Note on U5: Enter date the Contractor was notified of submittal disapproval (MM/DD/YY)