## Material Submittals Schedule
SCHEDULE OF MATERIAL SUBMITTALS | [14 empty] | PROJECT NUMBER QUUG 06-1003 |  | PROJECT TITLE RENOVATE MEETING HALL, B105 |  |  |  | SOLICITATION / CONTRACT NO.
(To be completed by Project Engineer) | [14 empty] | (To be completed by Contract Administrator)
LINE NUMBER | ITEM OR DESCRIPTION OF ITEM, CONTRACT REFERENCE, TYPE OF SUBMITTAL | NUMBER OF COPIES REQUIRED | [11 empty] | REQUIRED SUBMISSION DATE | DATE RECEIVED IN CONTRACTING | DATE TO CIVIL ENGINEERING | RETURN SUSPENSE DATE | SUBMITTAL NUMBERS | DATE CONTRACTOR NOTIFIED |  | CONTRACTOR RESUBMITTAL | FINAL APPROVAL | REMARKS
|  | CERTIFICATE OF COMPLIANCE | SHOP DRAWINGS | SAMPLES | COLOR SELECTION | MANUFACTURER'S RECOMMENDATION | MANUFACTURER'S WARRANTY | CATALOG DATA | OPERATING INSTRUCTIONS | SCHEDULES, LISTINGS, REPORTS, PLANS | TECHNICAL DATA | TEST REPORTS | FIELD REPORTS
[19 empty] | APPROVED | DISAPPROVED
SECTION 01 11 01 GENERAL CONDITIONS
1 | Warranty letter | [8 empty] | 4 |  |  |  | Acceptance+15
2 | Construction Schedule | [8 empty] | 4 |  |  |  | CNTP+7
3 | Progress Schedule | [8 empty] | 4 |  |  |  | CNTP+10
4 | Work Plan | [8 empty] | 4 |  |  |  | CNTP+7
5 | DD Form 1354 | [8 empty] | 4 |  |  |  | FI+15
6 | As-Built drawings | [8 empty] | 4 |  |  |  | FI+15
7 | Mobility Plan | [8 empty] | 4 |  |  |  | CNTP+15
8 | Project Sign | [8 empty] | 4 |  |  |  | CNTP+15
9 | Quality Control Plan | [8 empty] | 4 |  |  |  | CNTP+15
10 | Waste & construction debris management | [8 empty] | 4 |  |  |  | Final Inspection
11 | Key Staff | [8 empty] | 4 |  |  |  | DNTP+15
12 | Environmental Protection Plan | [8 empty] | 4 |  |  |  | CNTP+15
13 | Spatial Data | [8 empty] | 4 |  |  |  | As Built+10
14 | Health and safety Plan | [8 empty] | 4 |  |  |  | CNTP +15
PART 12 - SMALL PROJECT DESIGN-BUILD PROGRESS SCHEDULES
15 | Design-Build Schedule | [8 empty] | 1 |  |  |  | DNTP+10
16 | Monthly Updates | [8 empty] | 1 |  |  |  | Every 1st of month
SECTION 01 11 02 SPECIAL CONDITIONS
17 | Construction Schedule | [8 empty] | 1 |  |  |  | CNTP+7
18 | Work Plan | [8 empty] | 1 |  |  |  | CNTP+7
19 | Government furnished material request | [8 empty] | 1 |  |  |  | Work-15
20 | Inventory of the excess supplies, materials and equipment imported free duty | [8 empty] | 1 |  |  |  | Prior to FI
21 | Classification certificate | 1 | [11 empty] | CNTP+30
SECTION 02 41 00 DEMOLITION
22 | Progress schedule of the work | [8 empty] | 1 |  |  |  | CNTP + 15
23 | Demolition Plan | [8 empty] | 1 |  |  |  | CNTP + 15
24 | Management and disposal plan for waste from demolition | 1 | [7 empty] | 1 |  |  |  | CNTP+15
25 | Authorized dump or treatment and recovery plant | 1 | [11 empty] | CNTP+15
26 | Delivery and disposal certificate | 1 | [11 empty] | CNTP+15
SECTION 02 82 00 ASBESTOS REMEDIATION
27 | Respiratory protection equipment. | [6 empty] | 1
28 | All Individual Protective Equipment (EPI’s) used | [6 empty] | 1
29 | HEPA filtered vacuum cleaners | [6 empty] | 1
30 | Landfill Approval | 1
31 | Certificates on Risk Prevention training | 1
32 | Certificate of registration as Asbestos Risk | 1
33 | Certification of Industrial Hygienist responsible | 1
34 | Asbestos Hazard Abatement Plan | [11 empty] | 1
35 | Notifications | [8 empty] | 1
SECTION 02 84 16 HANDLING OF LIGHTING BALLASTS AND LAMPS CONTAINING PCBS AND MERCURY
36 | Qualifications of CIH | 1
37 | Training Certification | 1
38 | PCB and Lamp Removal Work Plan | 1
39 | PCB and Lamp Disposal Plan | 1
40 | Transporter certification | 1
41 | Certification of Decontamination | 1
42 | Certificate of Disposal and/or recycling | 1
43 | DD Form 1348-1 | [11 empty] | 1
44 | Testing results | [10 empty] | 1
SECTION 03 30 00 CAST IN PLACE CONCRETE
45 | Inspection certificate of the concrete batch plant. | 1
46 | Concrete Control Tests Program. | [10 empty] | 1
47 | Results of the concrete control tests. | [11 empty] | 1
48 | Polyethylene sheet catalog data. | [6 empty] | 1
49 | Quality Control Program | [8 empty] | 1
SECTION 04 20 00 MASONRY
50 | Manufacturer's Catalog Data | [6 empty] | 1
51 | Certificates | 1 | [9 empty] | 1
52 | Close-out Take Back Program | [7 empty] | 1
SECTION 05 12 00 STRUCTURAL STEEL
53 | Erection Plan |  | 1
54 | Welding Procedures and Qualifications | 1 | 1
SECTION 05 50 13 MISCELLANEOUS METAL FABRICATIONS
55 | Handrails |  | 1 |  |  |  | 1
56 | Access doors and panels, installation drawings | [5 empty] | 1
57 | Cover plates and frames, installation drawings |  |  | 1 |  |  | 1
58 | Steel welding inspection results | [5 empty] | 1 |  |  |  |  | 1
59 | Welding Procedures and Qualifications | 1
SECTION 07 22 00 ROOF AND DECK INSULATION
60 | Vapor Barrier |  |  |  |  | 1 |  | 1
61 | Lightweight Concrete | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
62 | Protective Fleece Layer | 1 |  | 1 |  |  |  | 1 |  |  |  | 1
63 | Waterproof Membrane |  |  | 1 |  | 1 |  | 1
64 | Waterproof Membrane | [5 empty] | 1 |  |  |  |  | 1
65 | Waterproof Fluid applied membrane | [5 empty] | 1 |  |  |  |  | 1
66 | Filtering tile | 1 |  | 1 |  |  |  | 1 |  |  |  | 1
67 | Flashing |  | 1
68 | Flashing |  |  |  |  | 1 |  | 1
69 | Heat Welding |  |  |  |  | 1
70 | Mastic | 1 | [5 empty] | 1 |  |  |  | 1
71 | Sealant for Expansion Joints | 1 | [5 empty] | 1 |  |  |  | 1
72 | Gutters and Downspouts |  |  |  |  | 1 |  | 1
73 | Fall Arresting System |  | 1
74 | Fall Arresting System | 1 | [5 empty] | 1
75 | Watertight test | [10 empty] | 1 | 1
SECTION 07 84 00 FIRESTOPING
76 | Fillers | [6 empty] | 1 | [5 empty] | NTP + 30
77 | Firestopper Products |  |  |  |  | 1 |  | 1 | [5 empty] | NTP + 30
SECTION 07 92 00 JOINT SELANTS
78 | Sealants, Primers and Bond Brakers |  |  |  | 1 |  |  | 1 | 1 |  |  |  |  | NTP + 30
SECTION 08 11 13 STEEL DOOR AND FRAMES
79 | Doors | 1 | 1 |  |  |  |  | 1 | [5 empty] | NTP + 45
80 | Fireproof Doors |  | 1
81 | Frames | 1 | 1 |  |  |  |  | 1 | [5 empty] | NTP + 45
82 | Accessories | 1 | 1 |  |  |  |  | 1 | [5 empty] | NTP + 45
SECTION 08 14 00 WOOD DOORS
83 | Manufacture's Catalog Data | [6 empty] | 1 | [5 empty] | NTP + 45
84 | Certificates of Fireproofing | 1 | [11 empty] | NTP + 45
SECTION 08 51 20 ALUMINUM WINDOWS
85 | Aluminum windows | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  |  | NTP + 45
86 | Frames | 1 | 1 |  |  |  |  | 1 | [5 empty] | NTP + 45
87 | Accessories | 1 | 1 |  |  |  |  | 1 | [5 empty] | NTP + 45
SECTION 08 71 00 DOOR HARDWARE
88 | Hardware (locks, hinges, closers, master keying, etc) |  |  |  |  | 1 |  | 1
89 | Hardware (locks, hinges, closers, master keying, etc) | [7 empty] | 1
90 | Hardware (locks, hinges, closers, master keying, etc) | [8 empty] | 1 |  |  |  | NTP + 60
SECTION 08 81 00 GLAZING
91 | Glazing | 1 |  | 1 | [9 empty] | NTP + 60
SECTION 09 24 23 CEMENT STUCCO
92 | Portland Cement Characteristics | [6 empty] | 1 | [5 empty] | NTP + 30
93 | Mortar additives | [6 empty] | 1 | [5 empty] | NTP + 30
94 | Bonding Bridge | [6 empty] | 1
95 | Fiber Reinforcing Mesh | [6 empty] | 1
SECTION 09 29 00 GYPSUM BOARD
96 | Water resistant gypsum boards | [6 empty] | 1
97 | Gypsum board | 1 | [5 empty] | 1
98 | Suspension system | [6 empty] | 1
99 | Instructions | [7 empty] | 1
100 | Asbestos Free Materials | 1
SECTION 09 30 00 CERAMIC TILES
101 | Manufacturer's Catalog Data | [6 empty] | 1
102 | Ceramic wall tile. |  |  | 1 |  |  |  |  | 1
103 | Ceramic floor tile |  |  | 1 |  |  |  |  | 1
SECTION 09 51 00 ACOUSTICAL CEILINGS
104 | Acoustic Ceiling | 1 | 1 | 1 |  |  |  | 1
SECTION 09 65 00 RESILIENT FLOORING
105 | Vinyl sheet flooring |  |  | 1 |  |  |  | 1
106 | Resilient wall base and accessories |  |  | 1 |  |  |  | 1
107 | Fire test performance | 1
108 | Bond and Moisture Tests | 1
109 | Operation and Maintenance Data | [7 empty] | 1
110 | Moisture, alkalinity and bond tests | [10 empty] | 1
SECTION 09 84 20 ACOUSTICAL WALL PANELS
111 | Acoustical Panels details |  | 1
112 | Acoustical Panels |  |  | 1 |  |  |  | 1
113 | Warranty | 1
SECTION 09 90 00 PAINTING AND COATING
114 | Coatings | 1 | [6 empty] | 1
115 | Lead content | [10 empty] | 1
116 | Deliverty Tickets | 1
SECTION 10 28 00 TOILET ACCESSORIES
117 | Recessed wash basin (java) and accessories | [6 empty] | 1 | [5 empty] | NTP + 45
118 | Recessed Wash Basin for handicapped persons | [6 empty] | 1 | [5 empty] | NTP + 45
119 | WC Bowl and Accesories | [6 empty] | 1 | [5 empty] | NTP + 45
120 | Urinal and accessories | [6 empty] | 1 | [5 empty] | NTP + 45
121 | Bathroom Hanger Accesories | [6 empty] | 1 | [5 empty] | NTP + 45
122 | Plate Glass Mirror | [6 empty] | 1 | [5 empty] | NTP + 45
123 | Mirror for handicapped persons restroom | [6 empty] | 1 | [5 empty] | NTP + 45
124 | Toilet roll dispenser. | [6 empty] | 1 | [5 empty] | NTP + 45
125 | Soap holder | [6 empty] | 1 | [5 empty] | NTP + 45
126 | Not used
127 | Soap Dispenser for handicapped toilet | [6 empty] | 1 | [5 empty] | NTP + 45
128 | Soap Dispenser for male and female toilets | [6 empty] | 1 | [5 empty] | NTP + 45
129 | Paper towel dispenser | [6 empty] | 1 | [5 empty] | NTP + 45
130 | Not used
131 | Grab bar for handicapped perons | [6 empty] | 1
132 | Water Cooler Drinking Fountain | [6 empty] | 1 | [5 empty] | NTP + 45
133 | Not used
SECTION 10 44 16 FIRE EXTINGUISHERS
134 | Fire Extinguishers | 1 | [5 empty] | 1
135 | Cabinets | [6 empty] | 1
136 | Wall Brackets | [6 empty] | 1
SECTION 13 48 73 SEISMIC CONTROL FOR MECHANICAL EQUIPMENT
137 | Bracing |  | 1 |  |  |  |  | 1
138 | Resilient Vibration Isolation Devices
139 | Equipment Requirements |  | 1 |  |  |  |  | 1
140 | Anchor Bolts | [10 empty] | 1
SECTION 21 13 13.00 10 WET PIPE SPRINKLERS SYSTEM, FIRE SUPPRESSION
141 | Automatic sprinklers | [6 empty] | 1
142 | Control station for sprinklers | 1 | [5 empty] | 1
143 | Water motor alarm | [6 empty] | 1
144 | Waterflow detector | [6 empty] | 1
145 | Piping and Accessories | 1 | [5 empty] | 1
146 | Pipe Hangers and Supports | [6 empty] | 1
147 | Double Check Valve Assembly (DCVA) | [6 empty] | 1
148 | Butterfly valve | [6 empty] | 1
149 | Fire department connection | [6 empty] | 1
150 | Tamper switch | [6 empty] | 1
151 | Pressure switch on retard chamber | [6 empty] | 1
152 | Gate valve and indicator posts | [6 empty] | 1
153 | Underground piping and components | [6 empty] | 1
154 | Qualification of installer | 1
155 | Specialized fire protection engineer | 1
156 | Sprinkler system hydraulic calculation | [8 empty] | 1
157 | Sprinkler heads and system layout |  | 1
158 | As-Built drawings |  | 1
159 | Operating and Maintenance (O&M) Instructions | [7 empty] | 1
SECTION 20 00 00 PLUMBING
160 | Rigid PVC piping | 1 | [5 empty] | 1
161 | PE100 Polyethylene piping and connection fittings. | 1 | [5 empty] | 1
162 | Clamp connection | [6 empty] | 1
163 | Underground gate valve and valve box | [6 empty] | 1
164 | Galvanized steel pipe DIN 2440 | 1
165 | Plastic piping (PP-R) | 1 | [5 empty] | 1
166 | Ball valve | [6 empty] | 1
167 | Check valve | [6 empty] | 1
168 | Automatic air vent | [6 empty] | 1
169 | Water meter | [6 empty] | 1
170 | Hose bibb and hose connection vacuum breaker | [6 empty] | 1
171 | Backflow preventer (RPPD) | [6 empty] | 1
172 | Floor drain | [6 empty] | 1
173 | Recirculation pumps | [6 empty] | 1
174 | Hammer arrestors | [6 empty] | 1
175 | Thermostatic Mixing valve | [6 empty] | 1
176 | Dielectric Sleeve Fitting | [6 empty] | 1
177 | Pluming System | [7 empty] | 1
SECTION 23 07 00 THERMAL INSULATION FOR MECHANICAL SYSTEMS
178 | Refrigerant piping insulation | [6 empty] | 1
179 | Duct insulation | [6 empty] | 1
180 | Insulation aluminum jacket | [6 empty] | 1
SECTION 23 31 13.16 40 METAL DUCTS
181 | Exhaust and supply air intake grilles into the rooms. | [6 empty] | 1
182 | Outside air intakes / exhaust louvers | [6 empty] | 1
183 | Sheet metal for rectangular ducts. | [6 empty] | 1
184 | Sheet metal for circular ducts. | [6 empty] | 1
185 | Manual balancing dampers. | [6 empty] | 1
186 | Diffuser. | [6 empty] | 1
187 | Diffuser. | [8 empty] | 1
188 | Return Grills | [6 empty] | 1
189 | Return Grills | [8 empty] | 1
190 | Fire dampers | [6 empty] | 1
191 | Low leakage motorized damper | [10 empty] | 1
192 | Backdraft dampers | [10 empty] | 1
193 | Testing and balancing of ductwork systems. | [10 empty] | 1
194 | Quality Certificated | 1
195 | Operation and Maintenance Manuals | [7 empty] | 1
SECTION 23 35 19 AIR CONDITIONING SYSTEM AND EXHAUST SYSTEMS
196 | Dedicated Out Door Air System DX (DOAS) | [6 empty] | 1 |  |  |  | 1
197 | Direct Expansion AHU | [6 empty] | 1 |  |  |  | 1
198 | Direct Expansion Multi split or VRF system | [6 empty] | 1 |  |  |  | 1
199 | Direct Expansion Split system 1X1 | [6 empty] | 1 |  |  |  | 1
200 | Exhaust fans | [6 empty] | 1 |  |  |  | 1
201 | Copper pipes per refrigerants | [6 empty] | 1
202 | Operation and Maintenance Manuals | [7 empty] | 1
SECTION 26 20 00 INTERIOR DISTRIBUTION SYSTEM
203 | Receptacles (one of each type) | [6 empty] | 1
204 | GFI receptacles | [6 empty] | 1
205 | GFI receptacles | [11 empty] | 1
206 | Circuit Breakers | [6 empty] | 1
207 | Conduit and fittings (one of each type) | [6 empty] | 1
208 | Wires and cables | [6 empty] | 1
209 | Outlet boxes and covers | [6 empty] | 1
210 | Junction boxes | [6 empty] | 1
211 | Panel Board | 1
212 | Panel Board |  | 1
213 | Panel Board | [6 empty] | 1
214 | Surge Protective Device | [6 empty] | 1
215 | Surface raceways | [6 empty] | 1
216 | Network analyzer | [6 empty] | 1
217 | Labels | [6 empty] | 1
218 | Devices Plates | [6 empty] | 1
219 | Toggle switches | [6 empty] | 1
220 | Safety switches | [6 empty] | 1
221 | Electric power meter | [6 empty] | 1
222 | Emergency HVAC Shut-Off Push Buttons | [6 empty] | 1
223 | Intersystem bonding termination | [6 empty] | 1
224 | Occupancy sensor switches | [6 empty] | 1
225 | Damper actuators and transformers | [6 empty] | 1
226 | Audio visual conduit and junction boxes |  | 1
227 | 0.6/1 kV insulation test. | [11 empty] | 1
228 | Certificate of compliance of each panelboard | 1
229 | Electrical Systems | [7 empty] | 1
SECTION 26 41 00 LIGHTNING PROTECTION SYSTEM
230 | Air terminals | [6 empty] | 1
231 | Connection and terminations | [6 empty] | 1
232 | Components | [6 empty] | 1
233 | Ground rods | [6 empty] | 1
234 | Exothermic welding kits | [6 empty] | 1
235 | Overall lightning protection system |  | 1
236 | Each major component |  | 1
237 | Grounding system test | [10 empty] | 1
238 | Lightning protection system inspection | [10 empty] | 1
239 | Lightning protection system | [7 empty] | 1
SECTION 26 51 00 INTERIOR LIGHTING
240 | Lighting Fixture | [6 empty] | 1
241 | LED Light Sources | [6 empty] | 1
242 | Light occupancy / vacancy sensors and controllers | [6 empty] | 1
243 | LED Power Supply Units (Drivers) | [6 empty] | 1
244 | LED Emergency Drivers | [6 empty] | 1
245 | Operating test | [11 empty] | 1
246 | Warranty | 1
247 | Lighting control system | 1
248 | Lighting control system |  | 1
249 | Lighting control system | [7 empty] | 1
250 | Lighting System | [7 empty] | 1
SECTION 26 56 00 EXTERIOR LIGHTING
251 | LED luminaire | [6 empty] | 1
252 | Photocell | [6 empty] | 1
253 | Operating test | [11 empty] | 1
254 | Operational service | 1
255 | Warranty | 1
256 | Lighting System | [7 empty] | 1
257 | Exterior Lighting Control System | [7 empty] | 1
SECTION 27 10 00 BUILDING TELECOMMUNICATIONS CABLING SYSTEM
258 | Cable trays | [6 empty] | 1
259 | Conduits | [6 empty] | 1
260 | Labels | [6 empty] | 1
261 | Telecommunications Cabling and Pathway System | [7 empty] | 1
SECTION 28 31 76 INTERIOR FIRE ALARM AND MASS NOTIFICTION SYSTEM
262 | Smoke detector | [6 empty] | 1
263 | Heat detector | [6 empty] | 1
264 | Pull station (with outdoor box “double action” STI Stopper II) | [6 empty] | 1
265 | Duct Smoke detector | [6 empty] | 1
266 | Strobe and speaker combined – FA | [6 empty] | 1
267 | Strobe and speaker combined – MNS | [6 empty] | 1
268 | Exterior Strobe and speaker combined – FA | [6 empty] | 1
269 | Radio Fire Alarm Transmitter BT-XM | [6 empty] | 1
270 | Fire damper detector | [6 empty] | 1
271 | Retarding chamber switch | [6 empty] | 1
272 | FACP/MNS EST4 | [6 empty] | 1
273 | Remote LCD Text Display | [6 empty] | 1
274 | Antenna | [6 empty] | 1
275 | Control panel interior wiring diagrams. |  | 1
276 | Point-to-point wiring diagrams |  | 1
277 | Battery power calculations |  | 1
278 | Nameplates |  | 1
279 | Instructions |  | 1
280 | Wiring Diagrams |  | 1
281 | System Operation |  | 1
282 | Notification Appliances |  | 1
283 | Amplifiers |  | 1
284 | Operation and Maintenance (O&M) Instructions | [7 empty] | 1
285 | Instruction of Government Employees | [7 empty] | 1
286 | Field Quality Control | [10 empty] | 1
287 | Testing Procedures | [10 empty] | 1
288 | System Operation | [11 empty] | 1
289 | Fire Alarm/Mass Notification System | [11 empty] | 1
SECTION 31 00 00 EARTHWORK
290 | Shoring |  | 1
291 | Borrow Site Testing | [10 empty] | 1
292 | Materials proposed as Backfill | [10 empty] | 1
293 | Materials proposed as Soil and Topsoil | [10 empty] | 1
SECTION 31 05 19 GEOTEXTILE
294 | Geotextile | [8 empty] | 1 | 1
295 | Execution control | [11 empty] | 1
SECTION 32 92 19 SEEDING
296 | Seed | [6 empty] | 1
297 | Fertilizer | [6 empty] | 1
298 | Topsoil | [6 empty] | 1
299 | Existing soil | [10 empty] | 1
SECTION 33 30 00 SANITARY SEWER
300 | PVC pipe and fittings. | [6 empty] | 1
301 | Round handhole. | [6 empty] | 1
302 | Round manhole. | [6 empty] | 1
303 | Round manhole frame and cover. | [6 empty] | 1
304 | Sewer pipe protection film and sealant. | [6 empty] | 1
SECTION 33 71 02 UNDERGROUND ELECTRICAL DISTRIBUTION
305 | Low voltage cable | [6 empty] | 1
306 | Ground rods | [6 empty] | 1
307 | Ground wires | [6 empty] | 1
308 | Exothermic Welding Cadweld | [6 empty] | 1
309 | Buried Warning and Identification Tape | [6 empty] | 1
310 | Handholes | [6 empty] | 1
311 | Handholes covers | [6 empty] | 1
312 | Conduits | [6 empty] | 1
313 | Field acceptance checks and tests | [10 empty] | 1
Note on T7: Enter date the Contractor was notified of submittal approval (MM/DD/YY)
Note on U7: Enter date the Contractor was notified of submittal disapproval (MM/DD/YY)

## Material Submittals Schedule
SCHEDULE OF MATERIAL SUBMITTALS | [14 empty] | PROJECT NUMBER QUUG 19-1003 |  | PROJECT TITLE CNS FINISHED WATER TANK |  |  |  | SOLICITATION / CONTRACT NO.
(To be completed by Project Engineer) | [14 empty] | (To be completed by Contract Administrator)
LINE NUMBER | ITEM OR DESCRIPTION OF ITEM, CONTRACT REFERENCE, TYPE OF SUBMITTAL | NUMBER OF COPIES REQUIRED | [11 empty] | REQUIRED SUBMISSION DATE | DATE RECEIVED IN CONTRACTING | DATE TO CIVIL ENGINEERING | RETURN SUSPENSE DATE | SUBMITTAL NUMBERS | DATE CONTRACTOR NOTIFIED |  | CONTRACTOR RESUBMITTAL | FINAL APPROVAL | REMARKS | submittals presentados por JJEXT
|  | CERTIFICATE OF COMPLIANCE | SHOP DRAWINGS | SAMPLES | COLOR SELECTION | MANUFACTURER'S RECOMMENDATION | MANUFACTURER'S WARRANTY | CATALOG DATA | OPERATING INSTRUCTIONS | SCHEDULES, LISTINGS, REPORTS, PLANS | TECHNICAL DATA | TEST REPORTS | FIELD REPORTS
[19 empty] | APPROVED | DISAPPROVED
SECTION 01 11 01 GENERAL CONDITIONS
1 | Warranty letter | [8 empty] | 1 |  |  |  | Acceptance+15
2 | Construction Schedule | [8 empty] | 1 |  |  |  | Contract Award+7 | [9 empty] | A
3 | Progress Schedule | [8 empty] | 1 |  |  |  | Contract Award+10
4 | Work Plan | [8 empty] | 1 |  |  |  | Contract Award+7 | [9 empty] | A
5 | DD Form 1354 | [8 empty] | 1 |  |  |  | Final Inspection-10
6 | As-Built drawings | [8 empty] | 1 |  |  |  | Final Inspection-5
7 | Mobility Plan | [8 empty] | 1 |  |  |  | Contract Award+15 | [9 empty] | A
8 | Project Sign | [8 empty] | 1 |  |  |  | Contract Award+15
9 | Quality Control Plan | [8 empty] | 1 |  |  |  | Final Inspection-15 | [9 empty] | A
10 | Waste & construction debris management | [8 empty] | 1 |  |  |  | Final Inspection
11 | Key Staff | [8 empty] | 1 |  |  |  | Final Inspection-15 | [9 empty] | A
12 | Environmental Protection Plan | [8 empty] | 1 |  |  |  | As-Built Drawings+10 | [9 empty] | NR
13 | Spatial Data | [8 empty] | 1 |  |  |  | Final Inspection-5
14 | Health and safety Plan | [8 empty] | 1 |  |  |  | Contract Award+15 | [9 empty] | A
SECTION 01 11 02 SPECIAL CONDITIONS
15 | Deliberate Risk Assessment Worksheet | [8 empty] | 1 |  |  |  | Contract Award+15
16 | Airfield Construction Requirements Checklist | [8 empty] | 1 |  |  |  | Contract Award+15
SECTION 02 41 00 DEMOLITION
17 | Demolition Plan | [8 empty] | 1 |  |  |  | CWC + 15 | [9 empty] | NR
18 | Existing conditions | [8 empty] | 1
19 | Authorized dump or treatment and recovery plant | 1
20 | Delivery and disposal certificate | 1
SECTION 03 30 00 CAST IN PLACE CONCRETE
21 | Polyethylene sheet catalog data | [6 empty] | 1
22 | Quality Control Program | [8 empty] | 1
23 | Concrete Mix design | [10 empty] | 1
24 | Slump Tests | [10 empty] | 1
25 | Compressive Strength Tests | [10 empty] | 1
26 | Inspection certificate of the concrete batch plant | 1
27 | Reinforcing Bars | 1
SECTION 04 20 00 MASONRY
28 | Bricks | 1 | [5 empty] | 1
SECTION 05 12 00 STRUCTURAL STEEL
29 | Erection and Erection Bracing Drawings |  | 1
30 | Fabrication Drawings Including Details of Connections |  | 1
31 | Direct Tension Indicator Washers | [6 empty] | 1
32 | Non-Shrink Grout | [6 empty] | 1
33 | Tension Control Bolts | [6 empty] | 1
34 | Bolts, Nuts, and Washers | [10 empty] | 1
35 | Direct Tension Indicator Washer Inspection Reports | [10 empty] | 1
36 | Manufacturer´s Qualifications | 1 | [9 empty] | 1
37 | Bolts, Nuts, and Washers | 1
38 | Bolts, Nuts, and Washers | 1
39 | Pins and Rollers | 1
40 | Welding procedures and qualifications | 1
41 | Quality control inspections | [11 empty] | 1
SECTION 05 50 13 MISCELLANEOUS METAL FABRICATIONS
42 | Handrails |  | 1 |  |  |  |  | 1 | [15 empty] | A
43 | Access doors and panels, installation drawings | [6 empty] | 1 | [15 empty] | A
44 | Cover plates and frames, installation drawings |  |  | 1 |  |  |  | 1 | [15 empty] | A
45 | Electrowelded hot-dip galvanized steel plate grating | [6 empty] | 1 | [15 empty] | A
46 | Steel welding inspection results | [10 empty] | 1 | [11 empty] | A
47 | Welding Procedures and Qualifications | 1 | [21 empty] | A
SECTION 07 00 00.01 FALL ARRESTING CLASS C ANCHORING DEVICE
48 | Drawings |  | 1
49 | Fall arresting system | [6 empty] | 1
50 | Rated capacity | [6 empty] | 1
51 | Calculations | [9 empty] | 1
52 | Manufacturer's installer accreditation | 1
53 | Manufacturer's certificate | 1
54 | Warranty | 1
55 | Spare Parts | 1
56 | Tensile Tests | [10 empty] | 1
57 | Operating instruction | [7 empty] | 1
SECTION 07 72 20 GRAVITY-TYPE ROOF VENTILATORS
58 | Roof Ventilators | [6 empty] | 1
59 | Manufacturers Warranty | [5 empty] | 1
SECTION 07 92 00 JOINT SEALANTS
60 | Sealants, Primers and Bond Breakers | [6 empty] | 1
SECTION 08 11 13 STEEL DOORS AND FRAMES
61 | Doors | 1 | 1 |  |  |  |  | 1
62 | Frames | 1 | 1 |  |  |  |  | 1
63 | Accessories | 1 | 1 |  |  |  |  | 1
SECTION 08 71 00 DOOR HARDWARE
64 | Hardware items | [6 empty] | 1 | 1 | 1
SECTION 09 90 00 PAINTING AND COATING
65 | Coatings | 1 | [6 empty] | 1
66 | Lead content | [10 empty] | 1
67 | Deliverty Tickets | 1
SECTION 09 97 13.16 INTERIOR COATING OF STEEL WATER TANKS
68 | Coating | [6 empty] | 1
69 | Roof joint sealant materials | 1 | [5 empty] | 1
70 | Coating sample collection and shipping kit | [10 empty] | 1
71 | Inspection Report | [10 empty] | 1
72 | Manufacturer Qualifications | 1
73 | Qualifications of Coating Contractors | 1
74 | Qualifications of QC Specialist Coating Inspector | 1 |  |  |  |  | 1
75 | Coating system instructions | [7 empty] | 1
SECTION 14 21 13 ELECTRIC TRACTION FREIGHT ELEVATORS
76 | Elevator Components |  | 1
77 | Wiring Diagrams |  | 1
78 | Elevator and Accessories | [6 empty] | 1
79 | Elevator Parts and Components | 1
80 | Endorsement Letter | 1
81 | Welders´Qualifications | 1
82 | Warranty | [5 empty] | 1
83 | Elevator | [7 empty] | 1
84 | Maintenance Control Program (MCP) | [7 empty] | 1
85 | Software and Documentation | [7 empty] | 1
SECTION 23 09 00 INSTRUMENTATION AND CONTROL (SCADA)
86 | Contractor Design Drawings |  | 1
87 | Programming Software | [6 empty] | 1
88 | Controller Application Programs | [6 empty] | 1
89 | Hardware | [6 empty] | 1
90 | Post-Construction Quality Control | [10 empty] | 1
91 | Start-Up Testing Report | [10 empty] | 1
92 | Integrator Qualifications | 1
SECTION 25 05 11 CYBERSECURITY FOR FACILITY RELATED CONTROL SYSTEM
93 | Network Communication Report |  | 1
94 | Cybersecurity Riser Diagram/Network Architecture Diagram |  | 1
95 | Wireless and Wired Broadcast Communication Request |  | 1
96 | Account Lock Exception Request |  | 1
97 | Multiple Ethernet Connection Device Request |  | 1
98 | Contractor Computer Cybersecurity Compliance Statements |  | 1
99 | Contractor Temporary Network Cybersecurity Compliance Statements |  | 1
100 | Cybersecurity Interconnection Schedule |  | 1
101 | Proposed STIG and SRG Applicability Report |  | 1
102 | Control System Cybersecurity Documentation | [6 empty] | 1
103 | Control System Cybersecurity Testing Procedures | [10 empty] | 1
104 | Control System Cybersecurity Testing Report | [10 empty] | 1
105 | Enclosure Keys | [10 empty] | 1
106 | Software and Configuration Backups | [10 empty] | 1
107 | Auditing Front End Software | [10 empty] | 1
108 | Device Audit Record Upload Software | [10 empty] | 1
109 | System Maintenance Tool Software | [10 empty] | 1
110 | Control System Scanning Tools | [10 empty] | 1
111 | STIG, SRG and Vendor Guide Compliance Result Report | [10 empty] | 1
112 | Control System Inventory Report | [10 empty] | 1
113 | Software Licenses | 1
114 | Accounts | [8 empty] | 1
115 | Hardware List | [8 empty] | 1
116 | Software List | [8 empty] | 1
117 | Questionnaire | [8 empty] | 1
SECTION 26 20 00 INTERIOR DISTRIBUTION SYSTEM
118 | Circuit Breakers | [6 empty] | 1
119 | Conduit and fittings (one of each type) | [6 empty] | 1
120 | Wires and cables | [6 empty] | 1
121 | Junction boxes | [6 empty] | 1
122 | Junction boxes |  | 1
123 | Panel Board | 1
124 | Panel Board |  | 1
125 | Panel Board | [6 empty] | 1
126 | Surge Protective Device | [6 empty] | 1
127 | Surface raceways | [6 empty] | 1
128 | Labels | [6 empty] | 1
129 | Safety switches | [6 empty] | 1
130 | Receptacles | [6 empty] | 1
131 | Dry-type pad-mounted transformers 15 kVA | [6 empty] | 1
132 | 0.6/1 kV insulation test. | [10 empty] | 1
133 | Electrical Systems | [7 empty] | 1
SECTION 26 41 00 LIGHTNING PROTECTION SYSTEM
134 | Air terminals | [6 empty] | 1
135 | Connection and terminations | [6 empty] | 1
136 | Components | [6 empty] | 1
137 | Ground rods | [6 empty] | 1
138 | Exothermic welding kits | [6 empty] | 1
139 | Overall lightning protection system |  | 1
140 | Each major component |  | 1
141 | Lightning Protection and Grounding system test | [10 empty] | 1
142 | Lightning protection system | [7 empty] | 1
SECTION 26 42 15 CATHODIC PROTECTION SYSTEM FOR THE INTERIOR OF STEEL WATER TANKS
143 | Drawings |  | 1
144 | Wiring and Schematic Diagrm |  | 1
145 | Equipment | [6 empty] | 1
146 | Components | [6 empty] | 1
147 | Anodes | [6 empty] | 1
148 | Permanent reference electrodes | [6 empty] | 1
149 | Anode junction boxes | [6 empty] | 1
150 | Cable and wire | [6 empty] | 1
151 | Spare Parts | [6 empty] | 1
152 | Anode Connecting Cables | [10 empty] | 1
153 | Rectifier Testing | [10 empty] | 1
154 | Field acceptance checks and tests | [10 empty] | 1
155 | Qualifications | 1
156 | Cathodic Protection Design Package | [9 empty] | 1
157 | Cathodic Protection System | [7 empty] | 1
158 | Training Course | [7 empty] | 1
SECTION 26 51 00 INTERIOR LIGHTING
159 | Lighting Fixture | [6 empty] | 1
160 | LED Light Sources | [6 empty] | 1
161 | Light occupancy sensors and controllers | [6 empty] | 1
162 | LED Power Supply Units (Drivers) | [6 empty] | 1
163 | LED Emergency Drivers | [6 empty] | 1
164 | Local / Regional materials | [6 empty] | 1
165 | Operating test | [10 empty] | 1
166 | Lighting tests | [10 empty] | 1
167 | Warranty | 1
168 | Useful life of light sources | 1
169 | Spare parts | 1
170 | Lighting control system |  | 1
171 | Lighting System | [7 empty] | 1
172 | Lighting Control System | [7 empty] | 1
SECTION 26 56 00 EXTERIOR LIGHTING
173 | LED luminaire | [6 empty] | 1
174 | Photocell | [6 empty] | 1
175 | Local / Regional materials | [6 empty] | 1
176 | LED Power Supply Units (Drivers) | [6 empty] | 1
177 | Obstruction lighting | [6 empty] | 1
178 | Obstruction lighting | [7 empty] | 1
179 | Operating test | [10 empty] | 1
180 | Provisions For Lighting Fixtures | [8 empty] | 1
181 | Warranty | 1
182 | Useful life of light sources | 1
183 | Warranty obstructions lights | 1
184 | Spare parts | 1
185 | Lighting System | [7 empty] | 1
186 | Exterior Lighting Control System | [7 empty] | 1
187 | Obstruction lighting | [7 empty] | 1
SECTION 31 00 00 EARTHWORK
188 | Shoring | [9 empty] | 1
189 | Analysis of the results | [10 empty] | 1
190 | Materials proposed as Backfill | [10 empty] | 1
191 | Materials proposed as Soil and Topsoil | [10 empty] | 1
SECTION 31 05 19 GEOTEXTILE
192 | Geotextile | [6 empty] | 1 |  |  |  | 1
193 | Execution control | [11 empty] | 1
SECTION 32 05 10 AGGREGATES
194 | Aggregates origin control | [9 empty] | 1 | 1
195 | Job mix formula | [10 empty] | 1
196 | Test section | [10 empty] | 1
197 | Acceptance control | [10 empty] | 1
SECTION 32 05 12 SOIL STABILIZED IN-SITU
198 | Underlaying Surface | [9 empty] | 1
199 | Water | [9 empty] | 1
200 | Cement Origin Control | 1 | [8 empty] | 1 | 1
201 | Soil Origin Control | [9 empty] | 1 | 1
202 | Job Mix Formula | [9 empty] | 1
203 | Test Section | [9 empty] | 1 | 1
204 | Execution Control | [9 empty] | 1 | 1
205 | Acceptance Control | [9 empty] | 1
SECTION 32 05 30 PRIME COAT
206 | Existing surface | [10 empty] | 1
207 | Prime coat origin control | [9 empty] | 1 | 1
208 | Coverage aggregate origin control | [9 empty] | 1 | 1
209 | Prime coat application rate to be applied | [10 empty] | 1
210 | Coverage aggregate application rate to be placed | [10 empty] | 1
211 | Execution control | [10 empty] | 1
SECTION 32 05 42 BITUMINOUS CONCRETE TYPE BITUMINOUS MIXES
212 | Control of origin of the bitumen | [9 empty] | 1 | 1
213 | Control of origin of the aggregates | [9 empty] | 1 | 1
214 | Control of origin of the filler | [9 empty] | 1 | 1
215 | Production plant | [10 empty] | 1
216 | Job mix formula | [10 empty] | 1
217 | Test section | [10 empty] | 1
218 | Paving plan | [8 empty] | 1
219 | Production control | [9 empty] | 1 | 1
220 | Placing and compaction control | [11 empty] | 1
221 | Acceptance control | [11 empty] | 1
SECTION 32 07 00 PAVEMENT MARKINGS
222 | CE certification of the painting. | 1
223 | CE certification of the glass microspheres | 1
224 | Signing system during the painting. | [8 empty] | 1
225 | Tests of verification. | [11 empty] | 1
SECTION 32 31 13.53 HIGH-SECURITY FENCES AND GATES
226 | Fence Fabric | 1 | [5 empty] | 1
227 | Posts | [6 empty] | 1
228 | Post Caps | [6 empty] | 1
229 | Braces | [6 empty] | 1
230 | Rails | [6 empty] | 1
231 | Tension Wire | [6 empty] | 1
232 | Barbed wire | [6 empty] | 1
233 | Barbed Wire Supporting Arms | [6 empty] | 1
234 | Stretcher Bars | [6 empty] | 1
235 | Wire Ties | [6 empty] | 1
236 | Ground rods | [6 empty] | 1
237 | Ground wires | [6 empty] | 1
238 | Static grounding cable reel | [6 empty] | 1
239 | Gounding system test | [10 empty] | 1
240 | Gate Assembly | [6 empty] | 1
241 | Gate Hardware and Accessories | [6 empty] | 1
SECTION 32 92 19 SEEDING
242 | Seed | [6 empty] | 1
243 | Fertilizer | [6 empty] | 1
244 | Topsoil | [6 empty] | 1
245 | Existing soil | [10 empty] | 1
SECTION 33 11 00 WATER UTILITY DISTRIBUTION PIPING
246 | Pipe, Fittings, Joints and Couplings | [6 empty] | 1
247 | Valves | [6 empty] | 1
248 | Electrowelded joining | [6 empty] | 1
249 | Turbine Type Meters | [6 empty] | 1
250 | Compound type meters | [6 empty] | 1
251 | Bacteriological Samples | [10 empty] | 1
252 | Leakage test | [10 empty] | 1
253 | Hydrostatic Test | [10 empty] | 1
SECTION 33 16 15 WATER STORAGE STEEL TANK
254 | Detail Drawings |  | 1
255 | Tank Installation |  | 1
256 | Piping and Valve Installation |  | 1
257 | Manufacturer's Technical Literature | [6 empty] | 1
258 | System Description | [6 empty] | 1
259 | Galvanized steel sheet | [6 empty] | 1
260 | PVC waterproofing sheet reinforced | [6 empty] | 1
261 | Roof panel | [6 empty] | 1
262 | Valves | [6 empty] | 1
263 | Pipe, Fittings, Joints and Couplings | [6 empty] | 1
264 | Sealants and Gaskets | [6 empty] | 1
265 | Disinfection Procedures | [6 empty] | 1
266 | Chlorination system | [6 empty] | 1
267 | Manufacturer's Design Analysis | [9 empty] | 1
268 | Tank Installation | [10 empty] | 1
269 | Testing of Valves and Piping | [10 empty] | 1
270 | Hydrostatic Test | [10 empty] | 1
271 | Leak Test | [10 empty] | 1
272 | Manufacturer's Qualifications | 1
273 | Lining and Coating | 1
274 | Shipping, Handling, and Storage | [7 empty] | 1
275 | Warranty | [5 empty] | 1
SECTION 33 40 00 STORMDRAINAGE UTILITIES
276 | Gratings | [6 empty] | 1
277 | Pipeline | [6 empty] | 1
278 | Culvert (headwall) | [6 empty] | 1
279 | Fittings | [6 empty] | 1
280 | Jointing materials | [6 empty] | 1
SECTION 33 71 02 UNDERGROUND ELECTRICAL DISTRIBUTION
281 | Low voltage cable | [6 empty] | 1
282 | Ground rods | [6 empty] | 1
283 | Ground wires | [6 empty] | 1
284 | Exothermic Welding Cadweld | [6 empty] | 1
285 | Buried Warning and Identification Tape | [6 empty] | 1
286 | Handholes | [6 empty] | 1
287 | Handhole Covers | [6 empty] | 1
288 | Conduits | [6 empty] | 1
289 | Field acceptance checks and tests | [10 empty] | 1
290 | Handhole and covers | 1
Note on T7: Enter date the Contractor was notified of submittal approval (MM/DD/YY)
Note on U7: Enter date the Contractor was notified of submittal disapproval (MM/DD/YY)

## MSS (Spanish) (hidden)
RESUMEN MUESTRAS DE MATERIAL | [14 empty] | NÚMERO PROYECTO: QUUG 06-1003 |  | TÍTULO DE PROYECTO: RENOVAR SALA DE REUNIONES , B 105 |  |  |  | SOLICITACIÓN / CONTRATO NO.
(A cumplimentar por el ingeniero del proyecto) | [14 empty] | (A cumplimentar por administrador del contrato)
LÍNEA NÚMERO | PARTIDA O DESCRIPCIÓN DE PARTIDA, REFERENCIA DEL CONTRATO, TIPO DE PRESENTACIÓN | NUMBER OF COPIES REQUIRED | [11 empty] | FECHA DE ENTREGA | FECHA RECEPCIÓN EN CONTRATACIÓN | FECHA EN INGENIERíA CIVIL | FECHA LÍMITE DE DEVOLUCIÓN | NÚMERO DE MUESTRA | FECHA NOTIFICACIÓN A CONTRATISTA |  | SEGUNDA PRESENTACIÓN DEL CONTRATISTA | APROBACIÓN FINAL | OBSERVACIONES
|  | CERTIFICADO DE CUMPLIMIENTO | PLANOS DE TALLER | MUESTRAS | SELECCIÓN DE COLOR | RECOMENDACIONES DEL FABRICANTE | GARANTÍA DEL FABRICANTE | DATOS DE CATÁLOGO | INSTRUCCIONES DE FUNCIONAMIENTO | PROGRAMAS, LISTADOS, INFORMES, PLANES | DATOS TÉCNICOS | PRUEBAS | INFORMES DE TRABAJOS DE CAMPO
[19 empty] | APROBADO | DESAPROBADO
SECCIÓN 01 11 01 CONDICIONES GENERALES
1 | Carta de garantía | [8 empty] | 4 |  |  |  | Acceptance+15
2 | Programa de obra | [8 empty] | 4 |  |  |  | CNTP+7
3 | Programa de avance de obra | [8 empty] | 4 |  |  |  | CNTP+10
4 | Plan de obra | [8 empty] | 4 |  |  |  | CNTP+7
5 | DD Form 1354 | [8 empty] | 4 |  |  |  | FI+15
6 | Planos As-Built | [8 empty] | 4 |  |  |  | FI+15
7 | Plan de movilización | [8 empty] | 4 |  |  |  | CNTP+15
8 | Proyecto firmado | [8 empty] | 4 |  |  |  | CNTP+15
9 | Plan de control de calidad | [8 empty] | 4 |  |  |  | CNTP+15
10 | Certificado de gestión de residuos y escombros | [8 empty] | 4 |  |  |  | Final Inspection
11 | Personal clave | [8 empty] | 4 |  |  |  | DNTP+15
12 | Plan de protección medioambiental | [8 empty] | 4 |  |  |  | CNTP+15
13 | Datos especiales | [8 empty] | 4 |  |  |  | As Built+10
14 | Plan de salud y seguridad | [8 empty] | 4 |  |  |  | CNTP +15
PART 12 - PROYECTOS PEQUEÑOS DESIGN-BUILD AVANCE DE OBRA
15 | Programa Design-Build | [8 empty] | 1 |  |  |  | DNTP+10
16 | No usado
SECCIÓN 01 11 02 CONDICIONES ESPECIALES
17 | Calendario de obra | [8 empty] | 1 |  |  |  | CNTP+7
18 | No usado
19 | Solicitud de material suministrado por el Gobierno | [8 empty] | 1 |  |  |  | Work-15
20 | Inventario del excedente de suministros, materiales y equipos importados libre de impuestos | [8 empty] | 1 |  |  |  | Prior to FI
21 | No usado
SECTION 02 41 00 DEMOLITION
22 | No usado
23 | Plan de demolición | [8 empty] | 1 |  |  |  | CNTP + 15
24 | Plan de gestión y eliminación de los residuos procedentes de la demolición | 1 | [7 empty] | 1 |  |  |  | CNTP+15
25 | Vertedero autorizado o planta de tratamiento y recuperación | 1 | [11 empty] | CNTP+15
26 | Certifica de cumplimiento | 1 | [11 empty] | CNTP+15
SECCIÓN 02 82 00 REMEDIOS PARA EL AMIANTO
27 | Equipo de protección respiratoria. | [6 empty] | 1
28 | Todos los Equipos de Protección Individual (EPI) utilizados | [6 empty] | 1
29 | Aspiradoras con filtro HEPA | [6 empty] | 1
30 | Aprobación de Relleno Sanitario | 1
31 | Certificados de formación en Prevención de Riesgos | 1
32 | Certificado de registro como Riesgo de Amianto | 1
33 | Certificación de Higienista Industrial responsable | 1
34 | Plan de reducción de riesgos de asbesto | [11 empty] | 1
35 | Notificaciones | [8 empty] | 1
SECCIÓN 02 84 16 MANIPULACIÓN DE BALASTOS DE ILUMINACIÓN Y LÁMPARAS QUE CONTIENEN PCB Y MERCURIO
36 | Cerfificados del CIH | 1
37 | Certificado de Capacitación | 1
38 | PCB y Plan de trabajo de eliminación de lámparas | 1
39 | Plan de eliminación de PCB y lámparas | 1
40 | Certificación de transporte | 1
41 | Certificación de descontaminación | 1
42 | Certificación de eliminación y/o reciclaje | 1
43 | DD Form 1348-1 | [11 empty] | 1
44 | Resultados de las pruebas | [10 empty] | 1
SECCIÓN 03 30 00 HORMIGÓN VERTIDO IN SITU
45 | Certificado de la inspección de la central de fabricación | 1
46 | Programa de ensayo de control de hormigón | [10 empty] | 1
47 | Resultado de los ensayos de control de hormigón | [11 empty] | 1
48 | Catálogo de la lámina de polietileno | [6 empty] | 1
49 | Programa de control de calidad | [8 empty] | 1
SECCIÓN 04 20 00 ALBAÑILERÍA
50 | Catálogos del fabricante | [6 empty] | 1
51 | No usado
52 | No usado
SECCIÓN 05 12 00 STRUCTURAL STEEL
53 | Levantamiento de planos |  | 1
54 | Procedimientos de soldadura y calificaciones | 1 | 1
SECCIÓN 05 50 13 FABRICACIONES VARIAS DE METAL
55 | Pasamanos |  | 1 |  |  |  | 1
56 | No usado
57 | No usado
58 | Resultados de inspección de soldadura de acero | [5 empty] | 1 |  |  |  |  | 1
59 | Procedimientos de soldadura y calificaciones | 1
SECCIÓN 07 22 00 CUBIERTA TRANSITABLE LOSA FILTRANTE
60 | Barrera de vapor |  |  |  |  | 1 |  | 1
61 | Hormigón aligerado | 1 |  |  |  | 1 |  | 1 |  |  |  | 1
62 | Lámina antipunzonamiento | 1 |  | 1 |  |  |  | 1 |  |  |  | 1
63 | Membrana de Impermeabilización |  |  | 1 |  | 1 |  | 1
64 | Membrana de Impermeabilización | [5 empty] | 1 |  |  |  |  | 1
65 | Membrana fluida impermeabilizante | [5 empty] | 1 |  |  |  |  | 1
66 | Losa filtrante | 1 |  | 1 |  |  |  | 1 |  |  |  | 1
67 | Remates |  | 1
68 | Remates |  |  |  |  | 1 |  | 1
69 | Soldadura en calor |  |  |  |  | 1
70 | Masilla | 1 | [5 empty] | 1 |  |  |  | 1
71 | Sellantes para juntas de dilatación | 1 | [5 empty] | 1 |  |  |  | 1
72 | Canalones y bajantes |  |  |  |  | 1 |  | 1
73 | Sistema de protección contra caídas de Alturas |  | 1
74 | Sistema de protección contra caídas de Alturas | 1 | [5 empty] | 1
75 | Prueba de estanqueidad | [10 empty] | 1 | 1
SECCIÓN 07 84 00 CORTAFUEGOS
76 | Información de productos | [6 empty] | 1 | [5 empty] | NTP + 30
77 | Instrucciones de fabricante |  |  |  |  | 1 |  | 1 | [5 empty] | NTP + 30
SECCIÓN 07 92 00 SELLANTES
78 | Sellantes, imprimación y desencofrantes |  |  |  | 1 |  |  | 1 | 1 |  |  |  |  | NTP + 30
SECCIÓNN 08 11 13 PUERTAS Y MARCOS DE ACERO
79 | Puertas | 1 | 1 |  |  |  |  | 1 | [5 empty] | NTP + 45
80 | Puertas Resistente al fuego |  | 1
81 | No usado
82 | No usado
SECCIÓN 08 14 00 PUERTAS DE MADERA
83 | Catálogos del fabricante | 1 | [5 empty] | 1 | [5 empty] | NTP + 45
84 | No usado | [12 empty] | NTP + 45
SECCIÓN 08 51 20 VENTANAS DE ALUMINIO
85 | Puertas y ventanas de aluminio | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  |  | NTP + 45
86 | No usado | [12 empty] | NTP + 45
87 | No usado | [12 empty] | NTP + 45
SECCIÓN 08 71 00 CERRAJERÍA
88 | Componentes de cerrajería |  |  |  |  | 1 |  | 1 | 1 | 1
89 | No usado
90 | No usado
SECCIÓN 08 81 00 ACRISTALAMIENTO
91 | Acristalamiento | 1 |  | 1 | [9 empty] | NTP + 60
SECCIÓN 09 24 23 ENFOSCADOS Y ENLUCIDOS
92 | Características del Cemento Portland | [6 empty] | 1 | [5 empty] | NTP + 30
93 | Aditivos del Mortero | [6 empty] | 1 | [5 empty] | NTP + 30
94 | Puente de Unión | [6 empty] | 1
95 | Malla de Fibra de refuerzo | [6 empty] | 1
SECCIÓN 09 29 00 TECHOS REGISTRABLES DE PLACA DE CARTÓN-YESO
96 | Placas de cartón-yeso resistente a la humedad | [6 empty] | 1
97 | Placas de cartón-yeso | 1 | [5 empty] | 1
98 | Sistema de Suspensión | [6 empty] | 1
99 | Instrucciones de fabricante | [7 empty] | 1
100 | Materiales exentos de Amianto | 1
SECCIÓN 09 30 00 AZULEJOS
101 | Datos del catálogo del fabricante | [6 empty] | 1
102 | Azulejos cerámicos |  |  | 1 |  |  |  |  | 1
103 | Pavimento cerámico |  |  | 1 |  |  |  |  | 1
SECCIÓN 09 51 00 TECHO ACÚSTICO SUSPENDIDO
104 | Sistema de falso techo | 1 | 1 | 1 |  |  |  | 1
SECCIÓN 09 65 00 SUELOS VINÍLICOS
105 | Lámina de suelo vinícica | 1 |  | 1 |  |  |  | 1
106 | Base de pared resistente y accesorios |  |  | 1 |  |  |  | 1
107 | No usado
108 | No usado
109 | No usado
110 | No usado
SECCIÓN 09 84 20 PANELES ACÚSTICOS DE PARED
111 | Detalles de paneles acústicos | 1 | 1 | 1 |  |  |  | 1
112 | No usado
113 | No usado
SECCIÓN 09 90 00 PINTURAS Y RECUBRIMIENTOS
114 | Pinturas | 1 | [6 empty] | 1
115 | Contenido de plomo | [10 empty] | 1
116 | Tickets de entrega | 1
SECCIÓN 10 28 00 SANITARIOS, ACCESORIOS DE BAÑO
117 | Lavabo y accesorios | [6 empty] | 1 | [5 empty] | NTP + 45
118 | Lavabo y accesorios para discapacitados | [6 empty] | 1 | [5 empty] | NTP + 45
119 | Inodoro y accesorios | [6 empty] | 1 | [5 empty] | NTP + 45
120 | No usado
121 | Perchas | [6 empty] | 1 | [5 empty] | NTP + 45
122 | Espejo | [6 empty] | 1 | [5 empty] | NTP + 45
123 | Espejo para discapacitados | [6 empty] | 1 | [5 empty] | NTP + 45
124 | Dispensador de papel higiénico | [6 empty] | 1 | [5 empty] | NTP + 45
125 | Jabonera | [6 empty] | 1 | [5 empty] | NTP + 45
126 | No usado
127 | Dispensador de jabón para WC discapacitados | [6 empty] | 1 | [5 empty] | NTP + 45
128 | Dispensador de jabón para baños masculinos y femeninos | [6 empty] | 1 | [5 empty] | NTP + 45
129 | Dispensador de papel | [6 empty] | 1 | [5 empty] | NTP + 45
130 | No usado
131 | Barra de apoyo | [6 empty] | 1
132 | Fuente enfriadora de agua para consumo | [6 empty] | 1 | [5 empty] | NTP + 45
133 | No usado
SECCIÓN 10 44 16 EXTINTORES
134 | Extintores | 1 | [5 empty] | 1
135 | Armarios | [6 empty] | 1
136 | Soportes de pared | [6 empty] | 1
SECCIÓN 13 48 73 CONTROL SÍSMICO PARA EQUIPOS MECÁNICOS
137 | Bracing |  | 1 |  |  |  |  | 1
138 | Dispositivos de aislamiento de vibraciones resistentes
139 | Requisitos de equipo |  | 1 |  |  |  |  | 1
140 | Pernos de anclaje | [10 empty] | 1
SECCIÓN 21 13 13.00 10 ROCIADORES DE TUBERÍAS HÚMEDA, EXTINCIÓN DE INCENDIOS
141 | Manerial y equipamiento | 1 | [5 empty] | 1
142 | No usado
143 | No usado
144 | No usado
145 | No usado
146 | No usado
147 | No usado
148 | No usado
149 | No usado
150 | No usado
151 | No usado
152 | No usado
153 | No usado
154 | Calificación del instalador | 1
155 | No usado
156 | Cálculos de aspesores del sistema hidráulico | [8 empty] | 1
157 | No usado
158 | Planos de taller |  | 1
159 | No usado
SECCIÓN 22 00 00 FONTANERÍA
160 | Sistama de Fontanería y equipamiento | 1 | [5 empty] | 1
161 | No usado
162 | No usado
163 | No usado
164 | No usado
165 | No usado
166 | No usado
167 | No usado
168 | No usado
169 | No usado
170 | No usado
171 | No usado
172 | No usado
173 | No usado
174 | No usado
175 | No usado
176 | No usado
177 | No usado
SECCIÓN 23 07 00 AISLAMIENTO TÉRMICO PARA SISTEMAS MECÁNICOS
178 | Aislamiento de tuberías de refrigerante | [6 empty] | 1
179 | No usado
180 | No usado
SECCIÓN 23 31 13.00 40 CONDUCTOS METÁLICOS
181 | Materiales de conductos | [6 empty] | 1 |  | 1
182 | No usado
183 | No usado
184 | No usado
185 | No usado
186 | No usado
187 | No usado
188 | No usado
189 | No usado
190 | No usado
191 | Amortiguador motorizado de baja fuga | [10 empty] | 1
192 | Amortiguadores de retroceso | [10 empty] | 1
193 | Prueba y equilibrado de sistemas de conductos | [10 empty] | 1
194 | No usado
195 | No usado
SECTION 23 35 19 SISTEMA DE IMPULSIÓN, DISTRIBUCIÓN, VENTILACIÓN Y EXTRACCIÓN DE AIRE
196 | Unidad esterior de aire dedicada sitema DX (DOAS) | [6 empty] | 1 |  |  |  | 1
197 | Unidad de expansión directa | [6 empty] | 1 |  |  |  | 1
198 | Sistema de expansion directa multi spplit o VRF | [6 empty] | 1 |  |  |  | 1
199 | Sistema de equipo partido 1x1 | [6 empty] | 1 |  |  |  | 1
200 | Extractores | [6 empty] | 1 |  |  |  | 1
201 | Tuberías de cobre y refrigerante | [6 empty] | 1
202 | No usado
SECCTÓN 26 20 00 SISTEMA DE DISTRIBUCIÓN INTERIOR
203 | Enchufes (uno de cada tipo) | [6 empty] | 1
204 | Enchufes GFI | [6 empty] | 1
205 | Enchufes GFI | [11 empty] | 1
206 | Interruptores de circuito | [6 empty] | 1
207 | Conductos y accesorios (uno de cada tipo) | [6 empty] | 1
208 | Cables | [6 empty] | 1
209 | Cajas y cubiertas de enchufes | [6 empty] | 1
210 | Cajas de unión | [6 empty] | 1
211 | Panel eléctrico | 1
212 | Panel eléctrico |  | 1
213 | Panel eléctrico | [6 empty] | 1
214 | Dispositivo de protección contra sobretensiones | [6 empty] | 1
215 | Canaleta de superficie | [6 empty] | 1
216 | Analizador de redes | [6 empty] | 1
217 | Etiquetas | [6 empty] | 1
218 | Placas de dispotitivos | [6 empty] | 1
219 | Intrruptor de palanca | [6 empty] | 1
220 | Interruptor de seguridad | [6 empty] | 1
221 | Medidor de potencia eléctrica | [6 empty] | 1
222 | Botones de apagado de emergencia hvac | [6 empty] | 1
223 | Terminación de unión entre sistemas | [6 empty] | 1
224 | Interruptores de sensores de ocupación | [6 empty] | 1
225 | Actuadores y transformadores de amortiguadores | [6 empty] | 1
226 | Conductos audiovisuales y cajas de conexiones |  | 1
227 | Prueba de aislamiento 0,6/1 kV. | [11 empty] | 1
228 | Certificado de cumplimiento de cada cuadro | 1
229 | Sistemas eléctricos | [7 empty] | 1
SECCIÓN 26 41 00 PROTECCIÓN CONTRA RAYOS
230 | Terminales aéreos | [6 empty] | 1
231 | Conexiones y terminaciones | [6 empty] | 1
232 | Componentes | [6 empty] | 1
233 | Varillas de tierra | [6 empty] | 1
234 | Kits de soldarura exotérmica | [6 empty] | 1
235 | Sistema de protección contra rayos |  | 1
236 | Cada elemento principal |  | 1
237 | Prueba del sistema de puesta a tierra | [10 empty] | 1
238 | Inspección del sistema de protección contra rayos | [10 empty] | 1
239 | Sistema de protección contra rayos | [7 empty] | 1
SECCIÓN 26 51 00 ILUMINACIÓN INTERIOR
240 | Luminarias | [6 empty] | 1
241 | Fuente de luz LED | [6 empty] | 1
242 | Control y sensores de ocupación de iluminación | [6 empty] | 1
243 | Unidades de alimentación LED | [6 empty] | 1
244 | Controladores de emergencia LED | [6 empty] | 1
245 | Prueba de funcionamiento | [11 empty] | 1
246 | Garantía | 1
247 | Sistema de control de iluminación | 1
248 | Sistema de control de iluminación |  | 1
249 | Sistema de control de iluminación | [7 empty] | 1
250 | Sistema de iluminación | [7 empty] | 1
SECCIÓN 26 56 00 ILUMINACIÓN EXTERIOR
251 | Luminarias LED | [6 empty] | 1
252 | Célula fotoeléctrica | [6 empty] | 1
253 | Puesta en servicio | [11 empty] | 1
254 | Servicio operativo | 1
255 | Garantía | 1
256 | Sistema de iluminación | [7 empty] | 1
257 | Sistema de Control de Iluminación Exterior | [7 empty] | 1
SECCIÓN 27 10 00 SISTEMA DE CABLEADO DE TELECOMUNICACIONES EN EDIFICIOS
258 | Bandeja de cables | [6 empty] | 1
259 | Conductos | [6 empty] | 1
260 | Etiquetas | [6 empty] | 1
261 | Sistema de canalización y cableado de telecomunicaciones | [7 empty] | 1
SECCIÓN 28 31 76 SISTEMAS DE ALARMAS CONTRAINCENDIOS INTERIOR Y NOTIFICACIÓN MASIVA
262 | Detector de humos | [6 empty] | 1
263 | Detector de calor | [6 empty] | 1
264 | Pulsador de alarma (con caja exterior“doble acción” STI Stopper II) | [6 empty] | 1
265 | Detector de humos de conductos | [6 empty] | 1
266 | Estroboscopio y altavos combinado – FA | [6 empty] | 1
267 | Estroboscopio y altavoz combinado – MNS | [6 empty] | 1
268 | Estroboscopio exterior y altavoz combinado– FA | [6 empty] | 1
269 | Radio BT-XM | [6 empty] | 1
270 | Compuerta cortafuego | [6 empty] | 1
271 | Interruptor con cámara de retardo | [6 empty] | 1
272 | AFCP/MNS EST4 | [6 empty] | 1
273 | Pantalla de texto LCD remota | [6 empty] | 1
274 | Antena | [6 empty] | 1
275 | Diagramas de cableado interior del panel de control. |  | 1
276 | Diagrama de cableado punto a punto |  | 1
277 | Cálculo de energía de la batería |  | 1
278 | Placas de equipo |  | 1
279 | Instrucciones |  | 1
280 | Diagrama de cableado |  | 1
281 | Funcionamiento del sistema |  | 1
282 | Dispositivos de notificación |  | 1
283 | Amplificadores |  | 1
284 | Manual de operaciones y mantenimiento | [7 empty] | 1
285 | Instrucciones para los empleados del Gobierno | [7 empty] | 1
286 | Informes de pruebas | [10 empty] | 1
287 | Procedimientos de pruebas | [10 empty] | 1
288 | Funcionamiento del sistema | [11 empty] | 1
289 | Sistema de alarmas de incendio/notificación masiva | [11 empty] | 1
SECCIÓN 31 00 00 MOVIMIENTO DE TIERRA
290 | Apuntalamiento |  | 1
291 | Pruebas de campo | [10 empty] | 1
292 | Materiales propuestos como Relleno | [10 empty] | 1
293 | Materiales propuestos como Suelo y Tierra vegetal | [10 empty] | 1
SECCIÓN 31 05 19 GEOTEXTIL
294 | Geotextile | [8 empty] | 1 | 1
295 | No usado
SECCIÓN 32 92 19 CÉSPED
296 | Semillas | [6 empty] | 1
297 | Fertilizante | [6 empty] | 1
298 | Terreno vegetal | [6 empty] | 1
299 | No usado
SECCIÓN 33 30 00 SANEAMIENTO
300 | Tuberías y accesorios de PVC | [6 empty] | 1
301 | Arquetas redondas | [6 empty] | 1
302 | Pozos redondos | [6 empty] | 1
303 | Marcos y tapas de pozos redondos | [6 empty] | 1
304 | Película protectora y sellador apra tuberías | [6 empty] | 1
SECCIÓN 33 71 02 INSTALACIONES ELÉCTRICAS ENTERRADAS
305 | Cable de baja tensión | [6 empty] | 1
306 | Picas de tierra | [6 empty] | 1
307 | Cables de tierra | [6 empty] | 1
308 | Soldadura exotérmica Cadweld | [6 empty] | 1
309 | Cinta de advertencia e identificación enterrada | [6 empty] | 1
310 | Arqutetas | [6 empty] | 1
311 | Tapas de arquetas | [6 empty] | 1
312 | Conductos | [6 empty] | 1
313 | Informes de prueba | [10 empty] | 1
Note on T7: Enter date the Contractor was notified of submittal approval (MM/DD/YY)
Note on U7: Enter date the Contractor was notified of submittal disapproval (MM/DD/YY)