## Submittals Schedule
SCHEDULE OF SUBMITTALS | [7 empty] | PROJECT # 25-1011 |  | PROJECT TITLE: REPAIR FENCE REFUELING PARKING AREA, F2420 |  |  |  |  | SOLICITATION / CONTRACT NO.
(To be completed by Project Engineer) | [7 empty] | (To be completed by Contract Administrator)
LINE NUMBER | ITEM OR DESCRIPTION OF ITEM, CONTRACT REFERENCE, TYPE OF SUBMITTAL | C = Construction Project D = Design Project | LAUGHLIN DIV 01 SPECIFICATIONS | ENVIRONMENTAL QUALITY CONSTRUCTION SPECIFICATIONS LAFB | STATEMENT OF WORK OR OBJECTIVES | NUMBER OF PAPER COPIES REQUIRED. DIGITAL COPIES ARE REQUIRED FOR ALL SUBMITTALS | REQUIRED SUBMISSION DATE | DATE RECEIVED IN CONTRACTING | DATE TO CIVIL ENGINEERING | RETURN SUSPENSE DATE | SUBMITTAL NUMBERS | DATE CONTRACTOR NOTIFIED |  | CONTRACTOR RESUBMITTAL | FINAL APPROVAL | REMARKS
[12 empty] | APPR | DIS
NTP 1 - AF Form 103
| Submit AF Form 103 | C | 2.2 |  | 2.6.7, 6.1, 6.4 |  | Submit 7 days after Notice to Proceed 1
| Submit completed and approved AF Form 103 |  | 2.2 |  | 2.6.7, 6.1, 6.4 |  | Within 49 days from NTP 1
| On-Site Investigation Agenda | D |  |  | 6.4 |  | 14 Calendar days prior to NTP 2
NTP 2 - Design
| Entry Access List (EAL) | D | 1.8.2 |  |  |  | 2 Weeks prior to base access
| Proof of OPSEC Training | D | 2.4 |  |  |  | 2 Weeks prior to base access
| Antiterrorism Level I Awareness Training | C, D | 2.4 |  |  |  | 2 Weeks prior to base access
| Summary of site investigation | D |  |  | 6.4 |  | NLT 14 Days after NTP 2
| 95% Design Package | D |  |  | 6.4 | 2 (drawings only) | NLT 42 days after Government approved 65% design submittal
| 100% Design Package | D |  |  | 6.4 | 2 (drawings only) | NLT 35 calendar days after Government approved 95% design submittal
| Statement of Work | D |  |  | 3.1.3.8 |  | NLT 35 calendar days after Government approved 95% design submittal
| Initial Progress Schedule | D | 6.1.1 |  |  |  | Within 5 Days after receiving NTP1
| Progress Schedule Form and Contract Progress Report | C, D | 6.1.1, 6.1.2 |  |  |  | Biweekly
| Meeting Minutes | D | 6.2.1 |  |  |  | NLT 3 Days after meeting
NTP 3 - Pre Construction
| Entry Access List (EAL) | C | 1.8.2 |  |  |  | 2 Weeks prior to base access
| Proof of OPSEC Training | C, D | 2.4 |  |  |  | 2 weeks prior to base access
| Contractor Safety Plan | C | 3.2.2 |  |  |  | NLT 30 days after NTP 3
| Certificate of Contractor Safety Compliance |  | 3.2.3 |  |  |  | NLT 7 days after NTP 3
| QC Manager Qualifications | C, D | 4.2.3 |  |  |  | NLT 7 days after NTP 3
| QC Plan | C, D | 4.2.4 |  |  |  | NLT 30 days after NTP 3
| Construction Site Plan |  | 12.1 |  |  |  | NLT 30 days after NTP 3
| Hazardous Material Approval (Safety Data Sheets) | C |  | 3.2.1 |  |  | NLT 30 days after NTP 3 (as required)
| Hazardous Waste Training Certificate |  |  | 3.2.2 |  |  | Prior to NTP 4 (as required)
| Hazardous Waste / Material Procedures |  |  | 3.2.2 |  |  | Prior to NTP 4 (as required)
| Public Water System Notification |  |  | 3.4.1 |  |  | NLT 30 days after NTP 3 (as required)
| Customer Service Inspection Certificate (TCEQ Form 20699) |  |  | 3.4.1 |  |  | Prior to NTP 4 (as required)
| TCEQ Public water system plan review submittal form (TCEQ Form 10233) |  |  | 3.4.1 |  |  | Prior to NTP 4 (as required)
| Clean Water Act TCEQ’s General Permit |  |  | 3.4.2 |  |  | Prior to NTP 4 (as required)
| Asbestos Hazard Abatement Plan |  |  | 3.5.2.1 |  |  | NLT 10 days prior to construction start
| Copy of notification to Department of State Health Services |  |  | 3.5.2.1 |  |  | NLT 10 days prior to construction start
| Worker/Area Protection Plan |  |  | 3.5.2.2 |  |  | Prior to NTP 4 (as required)
| FOD Plan | C | 14.1 |  |  |  | Prior to NTP 4 (as required)
| Traffic Control Plan | C, D | 12.2 | 5.3, 5.5 |  |  | NLT 30 Days after NTP 3
| Records of Existing Conditions | C, D | 1.5, 7.1.1 | 4.2, 4.4, 5.5 |  |  | NLT 30 Days after NTP 3
| Submittals per Contractor's Design SOW | D | 10.4.4 through 10.4.11 |  |  |  | TBD
NTP 4 - Construction
| Non-Hazardous Waste Disposal Manifest and/or Waste Shipment Record | C |  | 5.1 / 6.2 |  |  | NLT 45 days from the date of signature of receiving facility
| Hazardous Waste Disposal Manifests | C |  | 5.2 / 6.2 |  |  | As required, prior to removal from Government property
| Hazmat Usage Log | C |  | 6.1 |  |  | End of each month during construction
| QC Daily Inspection Reports | C | 4.2.6 |  |  |  | Weekly
| Progress Schedule Form and Contract Progress Report | C | 6.1 |  |  |  | Biweekly
| Meeting Minutes | C | 6.2.1 |  |  |  | NLT 3 Days after meeting
| Records of Existing Conditions | C | 7.1.1 |  |  |  | NLT 14 days after NTP 2
| Materials Testing | C | 7.1.3 |  |  |  | As required, within 7 days of test
| Submittals per Contractor's Design SOW | C | 10.4.4 through 10.4.11 |  |  |  | TBD
| Operation and Maintenance Data | C | 10.4.12 |  |  |  | NLT 2 weeks after Final Inspection
| As Built Drawings/CAD Files | C | 10.4.13 |  |  | 2 (D size) | NLT 2 weeks after Final Inspection
| Completion Inspection (QC Manager Punchlist) | C | 13.4 |  |  |  | NLT 3 days after Pre-Final Inspection
| Draft DD Form 1354 | C | 13.3 |  |  |  | Prior to Pre-Final Inspection
| Final DD Form 1354 | C | 13.3 |  |  |  | At Final Inspection
| Submittal registry at 95% | C |  |  | 3.1.6 |  | NLT 42 days after Government approved 65% design submittal
| Submittal registry at 100% | C |  |  | 3.1.6 |  | NLT 35 calendar days after Government approved 95% design submittal
| Construction Warranty Management Plan | C | 13.2 |  |  |  | NLT 2 weeks after Final Inspection
Project Specific Submittals
|  |  | N/A | N/A
|  |  | N/A | N/A
|  |  | N/A | N/A
|  |  | N/A | N/A
|  |  | N/A | N/A
|  |  | N/A | N/A
Schedule of Submittals Template, Feb 05 (SAF/AQCP)
Note on N7: Enter date the Contractor was notified of submittal approval (MM/DD/YY)
Note on O7: Enter date the Contractor was notified of submittal disapproval (MM/DD/YY)