DRAFT Task Order 1

NMMC Art Photography

Year 1 of Ordering Period under IDIQ contract M00264-26-D-XXXX

Terms and Conditions: All Terms and Conditions of the master IDIQ contract M00264-26-D-XXXX and its Performance Work Statement (PWS) are hereby incorporated and applicable to this Task Order.

- Purpose: The purpose of this task order is to complete an intake meeting and site visit to the NMMC Museum Support Facility (MSF) to discuss a schedule to photograph forty (40) works of art. Once a schedule is agreed to, the vendor shall photograph the 40 works and provide all required digital files to the NMMC Technical Point of Contact (TPOC).

- Tasks: The Contractor shall…

- Conduct a site visit at the NMMC Museum Support Facility (MSF) within 25 days of task order award. See PWS 3.1.1.

  - The site visit shall include an intake meeting with the TPOC.

  - The Contractor shall coordinate directly with the TPOC to schedule the site visit upon award of task order

  - The Contractor shall examine a sampling of the forty (40) works of art requiring services under this task order during the site visit and to review the workspace for photographing the collection.

  - This task is expected to take no more than 4 hours

- Photograph 40 works of art (See PWS 3.1.2, 3.1.3, 3.1.5)

  - Photograph each work of art and provide all required digital files according to the PWS 3.1.3

  - Provide one 4”x5” proof print of each digital file

  - Transmit all files to the TPOC via Dropbox

  - All images shall be included on an external hard drive after all photography has been completed for ordering period 1 of the contract

  - The list of forty (40) works of art to be photographed shall be provided at the intake meeting

- Period of Performance: The vendor shall submit completed digital files to the TPOC via Dropbox within ten (10) working days after the photography session. The printed proofs for each image shall be delivered via mail within thirty (30) days of completion of the photography session. The TPOC will review the digital files for color and clarity within five (5) working days and discuss any issues with the vendor.

All services under this task order shall be completed no later than 180 days after date of task order award.

| Task / Deliverable | Description | Period of Performance / Required Completion | Method of Delivery |
| --- | --- | --- | --- |
| Intake Meeting | See Section 2.a. | Within 25 days of task order award | Site visit at NMMC MSF |
| Photography of 40 works of Art | See Section 2.b.i | No later than 14 days after site visit | On site photography sessions at the MSF |
| Digital Files | See Section 2.b.i | No later than 10 days after photography session | Dropbox |
| 4”x5” Proof Prints | See Section 2.b.ii | No later than 30 days after photography session | Mail |

(End of Task Order)