# STATEMENT OF WORK – AMENDMENT 001

Battle of Bunker Hill 251st Commemoration

Event Management and Production Services

June 16–17, 2026 | Bunker Hill Monument, Charlestown, MA

| Solicitation Number | Contract Type | Period of Performance | Issuing Office |
| --- | --- | --- | --- |
| 140P4326Q0028 | FFP / Optional CLINs | Time of award – July 3, 2026 | Boston NHP, NPS |

# SECTION 1.0	SCOPE

## Purpose of Contract

The Contractor shall furnish all labor, transportation, materials, equipment, and supervision to support two (2) days of events — June 16 and June 17, 2026 — marking the 251st Anniversary of the Battle of Bunker Hill (BH251). These events are part of the America250 national commemorative programming and are expected to draw significant audiences including elected officials, international dignitaries, military leaders, veterans, students, and the general public.

The June 16, 2026 event will be a morning Naturalization Ceremony conducted by U.S. Citizenship and Immigration Services (USCIS), followed by the June 17, 2026 Remembrance Ceremony — the signature event of the BH251 commemoration — a fully produced program featuring speakers, living historians, military elements, and a wreath-laying ceremony, with the Bunker Hill Monument as its iconic backdrop.

All events take place outdoors, rain or shine, on the grounds of Bunker Hill Monument in the Southwest Quadrant. The contractor shall examine all conditions at the project site prior to submitting a proposal and is required to participate in a pre-event site visit with the Contracting Officer’s Representative (COR) within 48 hours post award.

## Contract Line Item Structure

This contract is structured with one (1) Firm Fixed-Price (FFP) base line item (CLIN 00010) covering the core physical infrastructure — tent, chairs, stage, and stage stairs with rail — and multiple additional Line Items (Base and Option CLINs) numbered 00020 through 00070 covering all other services and deliverables as follows:

| CLIN | Description | Type |
| --- | --- | --- |
| 00010 - Base | Core Physical Infrastructure: Tent (~300 people), Chairs (white ivory flat-bottom), Stage (12’Wx24’x3’H, Navy Skirting), Stage Stairs w/Rail | Firm Fixed-Price (FFP) $__________ |
| Included in 00010 - Base | Sound System Setup and Operation | Included in 00010 - Base |
| Included in 00010 – Base | Lighting Design and Operation | Included in 00010 - Base |
| Included in 00010 – Base | Media Platform (8’x12’x3’H) | Included in 00010 - Base |
| Included in 00010 – Base | ADA Compliant Stage | Included in 00010 - Base |
| Included in 00010 – Base | ASL Interpretation Services | Included in 00010 - Base |
| Included in 00010 – Base | Portable Restrooms (2 ADA Accessible + 2 Standard) | Included in 00010 - Base |
| Included in 00010 – Base | Tent Audio System | Included in 00010 - Base |
| Included in 00010 – Base | ADA Compliant Access Ramp (4’x24’) | Included in 00010 - Base |
| Included in 00010 – Base | Overnight Security Services (from time of setup through June 18, 2026) | Included in 00010 - Base |
| Included in 00010 – Base | Tent Sides Installation (installed at initial setup) | Included in 00010 - Base |
| Included in 00010 – Base | Event Management Services (non-setup/strike) | Included in 00010 - Base |
| Included in 00010 – Base | Tent Side Removal (between events) | Included in 00010 - Base |
| Included in 00010 – Base | Media Platform — Charlestown Navy Yard (8’x12’x3’H) | Included in 00010 - Base |
| Included in 00010 – Base | Noise Permitting w/ City of Boston — Bunker Hill | Included in 00010 - Base |
| Included in 00010 – Base | Video and Production Services — Bunker Hill | Included in 00010 - Base |
| Included in 00010 – Base | Low-Noise / Quiet Generator — set up and removal Bunker Hill | Included in 00010 - Base |
| Included in 00010 - Base | Draping/Piping Services — Event Setup/Breakdown (Approx. 125 L/F, Bunker Hill Lodge to Stage, VIP Speakers) | Included in 00010 - Base |
| 00020 – Base | First Amendment Barricade Setup (NPS supplied barricades for Bunker Hill location) (Fixed-Unit-Price per barricade; qty TBD) | Fixed-Unit-Price $___________ per unit |
| 00030 – Base | Barricade Rental — Bunker Hill (Fixed-Unit-Price per barricade; qty TBD) | Fixed-Unit-Price $___________ per unit |
| 00040 – Base | Barricade Rental — Charlestown Navy Yard (Fixed-Unit-Price per barricade; qty TBD) | Fixed-Unit-Price $___________ per unit |
| 00050 – Base | Barricade Setup and Breakdown — Charlestown Navy Yard (Fixed-Unit-Price per barricade; qty TBD) | Fixed-Unit-Price $___________ per unit |
| 00060 – Option 1 | Wooden Podium | Option 1 – FFP $___________ |
| 00070 – Option 2 | On-site Water Station | Option 2 – FFP $___________ |

## Applicable Laws and Insurance

All work under this contract shall be performed in accordance with applicable federal, state, and local laws, ordinances, rules, regulations, and standards. The selected contractor must be fully insured for general liability, property damage, and worker’s compensation for the entire contract period of performance. Proof of insurance shall be submitted to the CO/COR within 5 business days of award.

## Description of Project Site

Events are located on the grounds of Bunker Hill Monument, Monument Square, Charlestown neighborhood, Boston, Massachusetts (Southwest Quadrant). The monument and grounds are situated within a dense residential urban neighborhood with limited parking, narrow streets, and active residential traffic patterns. The contractor must account for noise management, community relations, and full compliance with City of Boston (including permitting with NPS and City of Boston) and Commonwealth of Massachusetts ordinances throughout the period of performance.

# SECTION 2.0	GENERAL

## Unforeseen Conditions

The Contractor shall notify the COR of any unforeseen needs or conditions that are beyond the scope of work detailed in Section 3.0. Substantial increases in scope will require a formal contract modification executed by the Contracting Officer (CO).

## Contractor Responsibilities

The contractor shall furnish all labor, transportation, materials, equipment, and supervision for services described in Base CLINs as a fully encompassing firm fixed-price obligation. All Optional CLINs, if exercised by the Government, shall be performed under the same terms and conditions.

## Availability

The contractor’s central office or authorized representative shall be available by phone weekdays, Monday through Friday, 8:00 AM to 4:30 PM Eastern Time, from the date of award through July 3, 2026. During the event days (June 16–17), the contractor’s on-site manager shall be reachable by radio and cell phone at all times.

## Pre-Event Site Visit

The selected contractor shall participate in a mandatory pre-event site visit with the COR within 48 hours of contract award. The contractor shall submit a written event execution plan to the COR within one (1) week of award, detailing proposed layouts, equipment lists, staffing plans, and logistics for all Base CLIN requirements and any exercised optional CLINs.

## Green Room — Bunker Hill Lodge

The Bunker Hill Lodge will serve as the designated green room for the morning event on both June 16 and June 17, 2026. The Contractor shall coordinate access and logistics for speakers, dignitaries, and performers with the COR and NPS facilities staff. Use of the Lodge as a staging and preparation area shall be incorporated into the event execution plan.

  - Events Covered Under This Contract

| Date | Event | Time | Location | Audience |
| --- | --- | --- | --- | --- |
| June 16, | Naturalization | 7:00 AM | SW Quadrant / | ~300 attendees |
| 2026 | Ceremony (USCIS) | – 11:00 | Monument Grounds |  |
|  |  | AM |  |  |
| June 17, | Morning Program (TBD) | 7:00 AM | SW Quadrant / | ~300 attendees |
| 2026 (AM) |  | – 11:00 | Monument Grounds |  |
|  |  | AM |  |  |
| June 17, | BH251 Remembrance | 1:00 PM | SW Quadrant / | ~300 seated + |
| 2026 (PM) | Ceremony — Signature | – 5:00 | Monument Grounds | overflow |
|  | Event | PM |  |  |

# SECTION 3.0	SCOPE OF WORK

## CLIN 00010 — Firm Fixed-Price (FFP): Core Physical Infrastructure

CLIN 00010 a Firm Fixed-Price portion of this contract and encompasses the following four (4) deliverables, all included as a single line item. The tent is provided as an open-top structure (top only, no sides). Tent sides, generator, permitting, and all other services are priced as Optional CLINs.

- Tent open-top structure (top only, no sides), to accommodate approximately 300 people weighted blocking only, no stakes are permitted on NPS property)

- Chairs - white ivory flat-bottom chairs to protect grass

- Stage 12’W x 24’ x 3’H with Navy blue skirting

- Stage Stairs with Rail features

### Site Plan Preparation and Event Coordination

The Contractor shall develop and submit for COR approval a comprehensive site plan illustrating the full layout for both June 16 and June 17 events. The plan shall address:

    - Audience seating configuration (approx. 300 white/ivory folding chairs with flat bottoms to protect the landscape)

    - Stage placement (12’ x 24’ x 3’ high) positioned to provide the Bunker Hill Monument as the primary backdrop for speakers and video/photo capture

    - Navy skirting on stage — stage stairs shall include rail features (Stage shall not have a rail)

    - Tent positioning (open-top, no sides, for approximately 300 attendees)

    - Traffic flow, accessible circulation, and entry/egress paths

    - Media, VIP, and general public zone delineation

    - Electrical, generator, and sound equipment placement (will require noise permitting with City of Boston in advance of events and be positioned on Street Monument Square).

### Generator — Low-Noise / Quiet Technology

The Contractor shall provide, install, and operate a low-noise (quiet-technology) generator (65–75 dBA) sufficient to power all event equipment. The Contractor shall be solely responsible for obtaining all required permits from the City of Boston and the Commonwealth of Massachusetts for generator use and fuel storage on NPS grounds, including all applicable MA DPU filings. Generator, fuel, and all associated permitting costs are included in the CLIN 00010 price. The Contractor shall coordinate placement with the COR and NPS grounds supervisor to prevent irrigation or landscape damage.

### Tent — Open-Top Structure (Rain or Shine)

The Contractor shall provide, install, and strike one (1) open-top tent (top only — no sides) sufficient to cover approximately 300 seated attendees. The tent shall:

    - Be configured for rain or shine weather conditions

    - Have Dura-Deck matting (or approved equivalent) placed beneath all tent footprint areas to protect turf and landscape

    - Require no tent stakes driven into park grounds — all anchoring must use ballast/weight systems

approved by the COR and NPS resources staff

    - Remain installed from setup date through June 18, 2026 (strike day)

### Stage Setup and Strike

The Contractor shall provide and install a stage meeting the following specifications:

    - Dimensions: 12 ft wide x 24 ft deep x 3 ft high

    - Positioned to allow unobstructed view of the Bunker Hill Monument as event backdrop

    - Navy blue stage skirting on all exposed sides

    - Stairway access with rail features

    - Formal stage seating — 12 stackable chairs minimum (coordinate layout with COR pre-event)

    - Stage setup as determined and proposed by contractor in site plan

Setup shall commence no earlier than June 12, 2026, unless otherwise approved by the NPS COR for earlier et up. Full setup (stage, tent, chairs) will begin as early June 12, 2026 (coordinate set up dates with COR). Strike shall be completed by June 18, 2026.

### Audience Seating

    - Provide and set up approximately 300 white/ivory folding chairs with flat (non-spike) bottoms to protect landscape

    - Chairs to remain on site between June 16 and June 17 (folded and stored within tent as needed)

    - Seating layout to be approved by COR prior to event day

### Meetings and Coordination

The Contractor shall attend all production, logistics, and security coordination meetings as required by the COR from the date of award through June 17, 2026.

# To Be Included in the FFP — Descriptions

Listed below are Firm-Fixed-Price tasks included in CLIN 00010.

## Sound System Setup and Operation

The Contractor shall determine all sound-related equipment needs, including wattage requirements, decibel standards for audience distance from stage, number of speakers, and any amplification needed based on audience size and site conditions. A sound board, mixer, and certified sound engineer shall be provided for both June 16 and June 17 events. The contractor shall ensure audio is properly directed with the Bunker Hill Monument as backdrop, avoiding excessive sound bleed into the surrounding residential neighborhood in compliance with City of Boston noise ordinances. Jacket mics and stationary mics are the preferred types of microphones required, but portable mics will be available if requested day of events.

## Lighting Design and Operation

The Contractor shall design and implement appropriate lighting for both events. June 17 shall include professional broadcast-quality lighting designed to provide even stage wash for press and production capture.

Lighting design shall be submitted to the COR for approval prior to installation.

## Media Platform (8’ x 12’ x 3’H) – Bunker Hill

The Contractor shall design, provide, and install a dedicated media/press platform measuring 8 ft x 12 ft x 3 ft high, positioned at a COR-approved location to provide an unobstructed sightline for press photography and video capture NO further than 40’ from speakers to ensure high quality.

## ADA Compliant Stage

The Contractor shall provide and install an ADA-compliant stage configuration, including all necessary modifications or supplemental equipment required to meet ADA accessibility standards for performers, speakers, and dignitaries with mobility needs. Specifications shall comply with applicable ADA standards and be reviewed and approved by the COR.

## ASL Interpretation Services

The Contractor shall arrange and provide certified American Sign Language (ASL) interpretation services for the full run of show on June 17, 2026 (1:00 PM – 5:00 PM). Interpreter(s) shall be positioned in a location with clear sightlines from the audience. Minimum one (1) primary interpreter and one (1) relief interpreter shall be provided.

## Portable Restrooms

The Contractor shall arrange drop-off and pick-up (no pumping/clean-out service required) of four (4) portable restroom units: two (2) ADA-accessible units and two (2) standard units. All units shall be fully stocked. No clean-up services are required (NPS will clean and re-stock in house as needed). Units shall be placed at a COR-approved location. Drop-off shall occur no later than June 15, 2026; pick-up no earlier than June 18, 2026.

## Tent Audio System

The Contractor shall provide and install an audio system within the tent to ensure adequate sound coverage for all attendees seated under the tent structure. Specifications shall be proposed by the Contractor and approved by the COR.

## ADA Compliant Access Ramp (4’ x 24’)

The Contractor shall provide and install one (1) ADA-compliant access ramp measuring 4 ft wide x 24 ft long, providing accessible entry to the stage for speakers and performers with mobility needs. The ramp shall comply with all applicable ADA standards and shall be reviewed and approved by the COR prior to installation.

## Overnight Security Services

The Contractor shall provide licensed security personnel to maintain overnight security of all contractor-furnished and Government properties including tent, stage, chairs, audio-visual equipment, and generator — from the time of initial setup through June 18, 2026. Security personnel must be licensed under Massachusetts General Laws and display proper identification at all times. NPS will maintain a security presence during event hours at no cost to the awardee.

### Tent Sides Installation

The Contractor shall furnish and install full-perimeter tent sides on the open-top tent provided under CLIN 00010. Tent sides shall be installed as part of the initial event setup, concurrent with tent installation. Sides shall be compatible with the tent structure, properly secured, and approved by the COR prior to installation. The type and material of the sides shall be proposed by the Contractor and approved by the COR. Installation shall use only ballast/weight-based anchoring per Section 9.3.

### Event Management Services (Non-Setup/Strike)

If exercised, the Contractor shall provide comprehensive on-site event management services covering all periods outside of initial setup and final breakdown. This includes on-site logistics coordination, vendor management, attendee flow management, real-time problem resolution, coordination with NPS staff and law enforcement, and overall event supervision during June 16 and June 17 events. Scope and staffing shall be proposed by the Contractor and approved by the COR.

Stage Management Services — MC and Event Operations

The Contractor shall provide a qualified Stage Manager / Master of Ceremonies (MC) who shall:

- Introduce all speakers from the NPS/COR-approved speaker list

- Cue all speakers, singers, bands, military elements, and ceremonial components for appropriate entrances and exits

- Coordinate all video operations with living historians and VIP speakers

- Develop an overall program timeline for COR approval, incorporating all speakers, music, military ceremonials, and planned media moments, and submit for approval at least 2 weeks prior to event date

- Choreograph and cue the ceremonial wreath-laying and any processional elements to ensure optimal media and public capture

- Manage all cue sheets in coordination with NPS staff

Attendee Welcome and Seating Services

The Contractor shall provide sufficient trained staff to welcome and direct all approved attendees on both June 16 and June 17. Staff shall:

- Greet arriving attendees at designated entry points

- Direct attendees to appropriate seating zones (general seating, accessible seating, VIP)

- Monitor seating capacity and manage crowd flow for safe occupancy

- Coordinate with NPS law enforcement rangers for security integration

### Tent Side Removal (Between Events)

The Contractor shall remove installed tent sides (if exercised under CLIN 00140) between the June 16 and June 17 events, as directed by the COR. Removal shall be completed by a time specified by the COR to ensure the tent is in the desired configuration for the subsequent event day. This CLIN covers labor and logistics for the interim removal and reinstallation, if needed.

Media Platform (8’ x 12’ x 3’H) — Pier 1 – Charlestown Navy Yard

The Contractor shall furnish and install a dedicated elevated media/press platform measuring 8 ft x 12 ft x 3 ft at the Charlestown Navy Yard for the mid-day USS Constitution turnaround event. The riser shall be positioned at a COR-approved location to provide press and production personnel with an unobstructed elevated view of the USS Constitution turnaround. Setup and strike shall be coordinated with Navy Yard facility personnel and the COR.

### Noise Permitting — Bunker Hill

The Contractor shall obtain all required noise variance permits and approvals from the City of Boston for amplified sound at the Bunker Hill event site. The Contractor shall manage all filings, coordination with City of Boston officials, and compliance with applicable noise ordinances for both event days. All permit fees and associated administrative costs are included in this CLIN price. The Contractor shall provide copies of all obtained permits to the COR prior to the event.

### Video and Production Services — Bunker Hill

The Contractor shall provide comprehensive video and production services for the Bunker Hill events on June 16 and June 17, 2026. Services shall include multi-camera broadcast-quality video production, post-production editing and delivery, and all associated technical personnel and equipment. Raw camera feeds and final edited deliverables shall be provided to the COR within ten (15) business days of event conclusion (no later than July 3, 2026). Full scope, deliverable specifications, and platform requirements shall be determined by the COR prior to or at time of option exercise.

Final deliverables shall include:

- Documentary video recording of June 16 Naturalization Ceremony

- High-quality broadcast footage — June 17 Remembrance Ceremony (full event, multi-camera)

- Raw camera feeds for immediate archival

- Post-event site walkthrough participation with COR and grounds supervisor to document any turf impacts; contractor is responsible for infill of approved soil and premium sun/shade grass seed in any damaged turf zones identified during walkthrough

All video deliverables shall conform to the following technical specifications:

- .mp4 file — full video output encoded as H.264, 1920 x 1080 pixels (HD)

- .srt file for closed captions

- Separate .mp4 file containing an audio-described version of the original video

### Low-Noise / Quiet Generator — Bunker Hill

If exercised, the Contractor shall provide, install, and operate a low-noise (quiet-technology) diesel generator rated at 65–75 dBA, sufficient to power all event equipment at the Bunker Hill site. The CLIN price includes generator rental (priced per day of use), all diesel fuel costs, and all required City of Boston and Commonwealth of Massachusetts (MA DPU) permitting fees for generator operation and fuel storage on NPS grounds. The Contractor shall be solely responsible for all permit filings and compliance. The Contractor shall coordinate generator placement with the COR and NPS grounds supervisor to prevent damage to irrigation systems or landscape. Generator shall be positioned on Monument Square Street as directed by the COR.

### Draping/Piping Services — Event Setup/Breakdown

If exercised, the Contractor shall provide and install pipe-and-drape systems for the event, including all setup and breakdown labor. The scope covers approximately 125 linear feet of draping routed from the Bunker Hill Lodge to the Stage to create a designated pathway and staging area for VIP speakers. Placement, configuration, and drape material shall be proposed by the Contractor and approved by the COR prior to installation. All installation shall use only ballast/weight-based anchoring and shall not damage turf, irrigation systems, or historic fabric.

CLIN 00020 – Base - First Amendment Barricade Setup (Fixed-Unit-Price Per Barricade; Quantity TBD)

The Contractor shall install Government furnished First Amendment (free speech) area interlocking steel barricades at the NPS-designated location on the event landscape. NPS will supply interlocking steel barricades for use under this CLIN. The Contractor is responsible for setup and strike only. Installation shall not damage turf, irrigation systems, or historic fabric. Placement shall be reviewed and approved by COR in consultation with NPS law enforcement. Pricing shall be a Fixed-Unit-Price on a per-barricade basis; the total quantity required is to be determined (TBD) by the COR and communicated at time of award.

### CLIN 00030 – Base - Barricade Rental — Bunker Hill (Fixed-Unit-Price Per Barricade; Quantity TBD)

The Contractor shall provide contractor-supplied interlocking steel barricade rental for the Bunker Hill event site. Pricing shall be a Fixed-Unit-Price on a per-barricade basis; the total quantity required is to be determined (TBD) by the COR and communicated at time of award. Barricades shall meet all applicable safety and crowd-control standards. Delivery, placement, and pickup shall be coordinated with the COR. This CLIN covers hardware rental only; setup and breakdown labor is priced under CLIN 00020.

### CLIN 00040 – Base - Barricade Rental — Charlestown Navy Yard (Fixed-Unit-Price Per Barricade; Quantity TBD)

The Contractor shall provide contractor-supplied interlocking steel barricade rental for the Charlestown Navy Yard event site. Pricing shall be a Fixed-Unit-Price on a per-barricade basis; the total quantity required is to be determined (TBD) by the COR and communicated at time of award. Barricades shall meet all applicable safety and crowd-control standards. Delivery, placement, and pickup shall be coordinated with the COR and Navy Yard facility personnel. This CLIN covers hardware rental only; setup and breakdown labor is priced under CLIN 00050.

### CLIN 00050 – Base - Barricade Setup and Breakdown — Charlestown Navy Yard (Fixed-Unit-Price Per Barricade; Quantity TBD)

The Contractor shall provide all labor required to set up and break down interlocking steel barricades at the NPS-designated First Amendment (free speech) area at the Charlestown Navy Yard. This CLIN covers contractor labor only; barricades may be NPS-supplied or contractor-supplied (see CLIN 00040), as directed by the COR. Installation shall not damage turf, irrigation systems, or historic fabric. Placement configuration shall be reviewed and approved by the COR in consultation with NPS law enforcement prior to installation. Pricing shall be a Fixed-Unit-Price on a per-barricade basis; the total quantity required is to be determined (TBD) by the COR and communicated at time of award.

OPTIONAL CLINs — Descriptions (CLINs 00060 through 00070)

All optional CLINs listed below are Firm-Fixed-Price line items. Each may be exercised individually or in any combination at the Government’s sole discretion.

## CLIN 00060 — Wooden Podium

If exercised, the Contractor shall provide and set up one (1) formal wooden podium on the main stage, with microphone attachment points compatible with the audio system provided under any exercised sound CLIN.

## CLIN 00070 — On-Site Water Station

If exercised, the Contractor shall provide and staff one (1) or more on-site water/hydration station(s) at approved locations on the event grounds, including tables, water dispensers, and cups. Placement shall be approved by the COR.

# SECTION 4.0	GOVERNMENT-FURNISHED PROPERTY

4.1

The Government will supply metal bike barricades as part of 1st amendment area at Bunker Hill. No additional materials, tools, or supplies will be provided to the awardee under this contract. All materials, equipment, and tools are Contractor-furnished from outside the park, except as specifically identified in the site plan or approved by the COR.

4.2

NPS will manage security for all daytime activities and provide law enforcement and non-law enforcement Rangers at each event for crowd control and public safety. NPS will coordinate with the Contractor’s stage manager and on-site supervisor.

## 4.3 First Amendment Barricades

NPS will supply First Amendment area interlocking metal barricades under CLIN 00020. Contractor is responsible for setup, positioning per NPS direction, and strike only. For contractor-supplied barricade rental (Bunker Hill and Charlestown Navy Yard), see CLINs 00030 and 00040. For contractor labor associated with 1st Amendment barricade setup/breakdown at Bunker Hill, see CLIN 00020, and for contractor labor associated with barricade setup/breakdown at Charlestown Navy Yard, see CLIN 00050.

# SECTION 5.0	SECURITY

5.1

All contractor employees shall carry and display government-issued or contractor-issued identification upon request. Identification shall be furnished by the contractor at no additional cost to the Government.

5.2

Contractor staff shall park vehicles only in areas designated by NPS park personnel. No contractor vehicles shall be parked on monument grounds. Deliveries requiring vehicle access shall be pre-coordinated with the COR.

5.3

Overnight security services will be provided by the contractor under CLIN 00010. NPS will manage all daytime security activities including setup and strike operations.

5.4

The Contractor shall notify the COR whenever on-site work is being performed. The Contractor shall take all necessary safety measures to ensure public safety throughout the period of performance.

# SECTION 6.0	PERIOD OF PERFORMANCE

6.1

The period of performance shall commence at time of award.. All work, including final recordings delivery and site restoration, shall be completed no later than July 3, 2026. Key milestones are as follows:

| Milestone | Description | Due Date |
| --- | --- | --- |
| Award | Contract Executed | TBD |
| Site Visit | Mandatory pre-event site visit with COR | Within 48 hrs post Award |
| Execution Plan | Written event execution plan submitted to COR | Within 1 week of Award |
| Setup Complete | All equipment, tent, stage, chairs in place | No Later Than June 15, 2026 |
| Event Day 1 | Naturalization Ceremony — USCIS (June 16) | June 16, 2026 |
| Event Day 2 AM | Morning Program (June 17) | June 17, 2026 |
| Event Day 2 PM | BH251 Remembrance Ceremony — Signature Event (June 17) | June 17, 2026 |
| Strike | All equipment removed, grounds restored | June 18, 2026 |
| Recordings Delivered | All video recordings submitted to COR | June 27 – July 3, 2026 |

## Final Site Map and Irrigation As-Builts

Final site map and irrigation as-builts will be provided upon award. The Contractor shall use these documents to finalize all layout and placement decisions for equipment, tent, stage, and ancillary items in coordination with the COR and NPS grounds supervisor.

## Contractor Site Plan Submission

In addition to Government-furnished site maps, the Contractor shall submit a proposed site plan to the COR for approval within one (1) week of award. The proposed site plan shall incorporate all information from the Government-furnished final site map and irrigation as-builts.

8.1

Public restrooms are available for contractor employee use during working hours.

8.2

All work shall be completed in a manner that creates no damage to surrounding Government property, historic structures, or landscape. The Contractor shall seek COR clarification for any ambiguous conditions. Any such damages will be the awardee’s responsibility to repair at no cost to the government. All such repairs must be completed within 10 days post event, in coordination with the COR, by licensed contractors.

8.3

Water and electrical power are NOT available on-site. The Contractor shall confirm electrical capacity with the prior to finalizing equipment selections. The Contractor shall include generator costs in the applicable CLIN price (see CLIN 00010 — Low-Noise / Quiet Generator).

8.4

Dumpsters for disposal of waste and recycling are available at the Charlestown Navy Yard. Only waste associated with performance of this contract shall be disposed of in NPS dumpsters.

# SECTION 9.0	RESTRICTIONS

9.1

No on-site work will be permitted outside of regular business hours (Monday–Friday, 7:00 AM–5:00 PM) except on the dates of scheduled special events, or in the days leading up to the events. All after-hours work must be pre-approved in writing by the COR, and approved prior to work being performed.

9.2

No parking of contractor vehicles will be allowed on the monument grounds. All deliveries requiring vehicle access shall be coordinated in advance with the COR to prevent damage to grounds and irrigation systems.

9.3

No tent stakes shall be driven into park grounds. No anchors shall be attached to trees or fences. Only ballast/weight-based anchoring systems are permitted. Any exceptions require written authorization from the COR in consultation with NPS resources staff.

9.4

Contractor may use lawns for installation of event equipment in coordination with the COR and NPS grounds supervisor. After events conclude, the Contractor shall participate in a walkthrough to identify any turf damage; etc. the Contractor is responsible for infill of NPS-approved soil and premium sun/shade grass seed in all damaged zones as part of the FFP price under CLIN 00010.

9.5

Contractor and all subcontractors shall not install any temporary or permanent device into the historic structure, monument, or historic objects on the Bunker Hill or Navy Yard premises.

— End of Statement of Work —